## CRS
Comment Resolution SHEET
|  |  | 043-F-DAT-00004-001 | Equipment Datasheet for Burner
BAPCO Modernization Program
No. | Rev. | Page No. | BAPCO's comment | SOC's Response | Disc. | Open/Close | Remark (Or Attachment)
1 | AP | 3 | Burner vendor shall be selected and finalised in consultation with and approval of Bapco. | Noted. | Stationary | Close |  | Syed Ahmed
2 | AP | 3 | Acid | To be updated. | Process | Close |  | Syed Ahmed
3 | AP | 3 | Sweet | To be updated. | Process | Close |  | Syed Ahmed
4 | AP | 4 | "in consultation and approval from Bapco to implement the best practice" | To be updated. | Process | Close |  | Syed Ahmed
5 | AP | 5 | move with above title. Adjust title to accumodate | To be updated. | Process | Close |  | Mohamed Ayyash
6 | AP | 6 | Align | To be updated. | Process | Close |  | Mohamed Ayyash
7 | AP | 6 | Use N and not n | To be updated. | Process | Close |  | Mohamed Ayyash