## 045-E-DAT-00002-001-RAP-CS1
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
2 | Text Box | Page 1 | Julio.Aguilar | Cover Page to comply with the Homogenization Procedure (000-A-PRO-50006-1) to be consistent with all OCs
3 | Callout | Page 2 | Saeed Taher | SA 240 TP 316L
4 | Callout | Page 2 | Salman Jaffer | Please confirm full vacuum or -10 psig per note 13
5 | Highlight | Page 2 | Salman Jaffer
6 | Callout | Page 2 | BD Mori | Specify the estimated highest temperature at transient operating conditions or upset scenario e.g start-up, shutdown, electrical power failure or any other operating scenario leading to the highest possible temperature expected at inlet to the air cooler. Based on the highest temperature if required the vendor shall perform FEA analysis.
7 | Text Box | Page 3 | Mahdi Ali | 3TGTU
8 | Text Box | Page 3 | Mahdi Ali | Equipment numbers to follow final EPC equipment numbering which is under review by Bapco team in SOC
9 | Callout | Page 3 | Salman Jaffer | a) Please refer to Bid Query T1383 for the requirement for automatic louver b) Type 'B' manifold. c) The degree of the slop for free draining purpose per PIDs
10 | Callout | Page 3 | BD Mori | Do not use acronyms: High Severity Wet H2S Service (HSS)
11 | Callout | Page 3 | Julio.Aguilar | add: according to BMPS-A3