## 047-A-PFD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Use the correct drawing nos.
2 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.
3 | Callout | 1 | balagangadhar.k | Secondary lines
4 | Callout | 1 | BD Mori | Keep the this line arrow direction same as FEED PFD. The steam pressure is acting on this vessel for level control
5 | Typewritten Text | 1 | MAK | s
6 | Typewritten Text | 1 | MAK | s
7 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 003
8 | Text Box | 1 | balagangadhar.k | 4
9 | Callout | 1 | Salman Jaffer | Destination of this stream is not consistence with the latest FEED PFD (BRB-228474 sheet 1 of 3 rev0 ) changes. The destination is TO FLARE. Please check and finalized the appropriate destination.
10 | Call-out | 1 | MAK | Enter the correct and whole equipment no.
11 | Callout | 1 | Salman Jaffer | Caustic from existing GTU
12 | Callout | 1 | balagangadhar.k | Show Carbon Canister
13 | Callout | 1 | Salman Jaffer | black valve NNF
14 | Callout | 1 | Salman Jaffer | Please refer to Bid Queries T1006 &T1102. Add stream number with composition in the H&M balance to show excess flow from BMP units to Existing units.
15 | Text Box | 1 | balagangadhar.k | SHEET No.
16 | Callout | 1 | balagangadhar.k | change PCV symbol, should be continuous line and bubble outside
17 | Callout | 1 | balagangadhar.k | Show Air cooler symbol as per LEGEND, this line to be deleted
18 | Text Box | 1 | balagangadhar.k | Change reboiler symbol as per legend, liquid baffle missing.
19 | Callout | 1 | balagangadhar.k | No dog legs, Move pump up
20 | Callout | 1 | Salman Jaffer | Please provide PFD number
21 | Text Box | 1 | balagangadhar.k | #50
22 | Callout | 1 | BD Mori | This Unit 047 PFDs shall be on hold until 1/2 SGP EDP/FEED is finalised. After that update unit 047 PFDs.
23 | Callout | 1 | balagangadhar.k | 1
24 | Callout | 1 | balagangadhar.k | Secondary lines
25 | Callout | 1 | Salman Jaffer | Replace LP steam with #50 Steam
26 | Callout | 1 | Salman Jaffer | Add a new note: Note 19, Ejectors 047H0001 A/B on 047V0001 to be used when operation mode is changed from Phenolic to Non-Phenolic.
27 | Callout | 1 | Salman Jaffer | PFD Number
28 | Call-out | 1 | MAK | Always show the border size A1
29 | Callout | 1 | BD Mori | Incorporate chimney tray numbers as per numbing philosophy
30 | Callout | 1 | Salman Jaffer | There are many sources in 7CDU/VDU not only Stabilizer. Please delete highlighted text.
31 | Callout | 1 | BD Mori | Provide reference to note 2
32 | Call-out | 1 | MAK | Always enter NTS for PFDs
33 | Text Box | 1 | balagangadhar.k | NNF
34 | Callout | 1 | balagangadhar.k | Note 3 is covered in 5SWS PFD where the common sump is located. Can be deleted here.
35 | Callout | 1 | balagangadhar.k | OFF
36 | Callout | 1 | balagangadhar.k | Indicate Main or secondary line - drafting
37 | Callout | 1 | balagangadhar.k | FHS
38 | Text Box | 1 | balagangadhar.k | 4
39 | Callout | 1 | balagangadhar.k | Remove Line