## 058-A-PFD-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | Refer to email sent to BMPEPC-temp for CON-BMP-EML-000046 - Project Document Coding for Existing UNITs as per WBS. For revamp drawings, TTSJV shall add sheet number instead of creating a new drawing number. the 50,000 series sequence number shall only be used for new drawings and is not applicable for PFD or PIDs.
2 | Callout | 1 | BD Mori | As per Fuel Gas BOD these vessels are names as Microscrubber. Two vessels, indicated them separately.
3 | Callout | 1 | BD Mori | In 2/3 BAGRU PFD temperature is 124°F. Check and correct inconsistence.
4 | Cloud+ | 1 | 986131 | - Write the equipment number for the vessel. This comment applier to the other three Pig Launcher/ receivers shown on this PFD - Update BMPS-A-50003 with the symbol for Pig Launcher/ Receiver - Update the Equipment Code in BMPS-A-50003 for Pig launcher/r
5 | Call-out | 1 | 986131 | Show bidirectional arrow if this line is intended for both receiving and sending
6 | Call-out | 1 | Ali Hasan | delete the valve
7 | Call-out | 1 | Ali Abbas | show arrow direction
8 | Call-out | 1 | Ali Hasan | This symbol is similar to reboiler. Please use different symbol. Refer to Owner P&ID BRA-80070 Sht. 1 at unit 061 for your reference.
9 | Call-out | 1 | Ali Hasan | Show the two vessels separately and show the interconnecting lines between them.
10 | Call-out | 1 | Ali Hasan | Change to Microscrubber and update datasheets and P&IDs
11 | Call-out | 1 | Ali Hasan | Revise the Note: The line shall be designed for operating pressure of 660 psig. However, the line shall be designed for 1200 psig.