## 073-A-BOD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out |  | Ali Hasan | As discussed in our meeting dated 30 March 2018 with the ROC-Offsite, the LSFO flare load data shall be verified and updated considering the following: The flared gases from the No.1 Sulphur Plant in LSFO (3&4 SRUs | 3&4 SWSs | 2TGTU and OGTU) are currently routed to either High-Level Remote Flare (HLRF) or LSFO flare. The HLRF will be de-commissioned post BMP | which is in BMP scope of work. Hence | the flared gases from these units will only be routed to LSFO flare. This needs to be included in the design basis.
2 |  |  |  | All backup documentation supporting the flare load data shall be included (attached) in the process design basis for reference. The 2HDU PSA purge gas flare load data to be included in the design capacity of LSFO flare post-BMP.
3 |  |  |  | Evaluate flare scenarios to ensure that the purge gas routing does not affect the Governing case under any scenario.
4 | Microsoft Word - Code 3 With Comments |  | Adel
5 | Rectangle |  | Jeung.Kim
6 | Arrow |  | Jeung.Kim
7 | Text Box |  | Jeung.Kim | Duplicated numbering
8 | Arrow |  | Mohamed Ayyash
9 | Typewritten Text |  | Mohamed Ayyash | 1.1
10 | Arrow |  | Mohamed Ayyash
11 | Typewritten Text |  | Mohamed Ayyash | 1.1.1
12 | Arrow |  | Mohamed Ayyash
13 | Arrow |  | Mohamed Ayyash
14 | Typewritten Text |  | Mohamed Ayyash | Delete dots from all sub numbers
15 | Call-out |  | Hasan Al Noaimi | To LSFO Flare
16 | Line |  | Mohamed Ayyash
17 | Typewritten Text |  | Mohamed Ayyash | will
18 | Arrow |  | Mohamed Ayyash
19 | Call-out |  | Hasan Al Noaimi | No 1 Hydrogen Plant
20 | Call-out |  | Hasan Al Noaimi | SRU 3 and 4
21 | Call-out |  | Hasan Al Noaimi | 2TGTU Tail Gas Treating Unit
22 | Typewritten Text |  | Mohamed Ayyash | 1
23 | Callout |  | rob.urban | What needs to be confirmed?
24 | Arrow |  | rob.urban
25 | Callout |  | rob.urban | What about the 2HDU depressuring load?
26 | Callout |  | rob.urban | What is the governing case? 2HDU is the largest molar flow
27 | Arrow |  | rob.urban
28 | Typewritten Text |  | Mohamed Ayyash | 1
29 | Line |  | Mohamed Ayyash
30 | Typewritten Text |  | Mohamed Ayyash | are reported
31 | Arrow |  | Mohamed Ayyash
32 | Callout |  | rob.urban | 40% is too conservative. 50% is generally used.
33 | Arrow |  | rob.urban
34 | Typewritten Text |  | Mohamed Ayyash | Verify, not clear
35 | Pen |  | Mohamed Ayyash | " WOBATFJZSVYIGKNA" |  | Arrow | Page 7 | Unlocked | None | Unchecked | Mohamed Ayyash | 2018-04-02 12:59 | #0000FF