## 083-A-BOD-00001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Nalini Mohan | This BOD is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequent deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. BOD shall be modified to incorporate the updated details from equipment supplier and further studies by the Contractor.
2 | Callout | 3 | BD Mori | This BOD can not be finalised based on the preliminary estimates at FEED stage. Therefore, TTSJV shall estimate the accurate nitoegn consumption for the design of the nitrogen plant and resubmit the BOD for Bapco review and approval.
3 | Call-out | 3 | Hasan Al Noaimi | and inerting
4 | Call-out | 3 | Mahdi Ali | General Note: The word 'New' shall not be used as per the BMPS-A8
5 | Text Box | 4 | Edgardo | shall
6 | Call-out | 4 | Edgardo | change to "shall include in"
7 | Text Box | 4 | Edgardo | shall
8 | Call-out | 4 | Edgardo | change to "safe access"
9 | Callout | 4 | BD Mori | Correct unit number.
10 | Callout | 5 | Nalini Mohan | Contractor to utilize existing Unit details to finalize the hydraulic /mechanical checks
11 | Call-out | 5 | Mahdi Ali | Use New numbering format as per BMPS-A8
12 | Callout | 5 | BD Mori | Outcome of this study shall be incorporated in the BOD.
13 | Callout | 6 | BD Mori | The process description shall be revised based on the Nitrogen Plant supplier's process description and resubmit the BOD for Bapco's review and approval.
14 | Callout | 8 | BD Mori | Revise these paragraphs based on the Nitrogen Plant supplier inputs.
15 | Callout | 9 | BD Mori | The process description shall be revised based on the Nitrogen Plant supplier's process description and resubmit the BOD for Bapco's review and approval.
16 | Callout | 10 | BD Mori | shall
17 | Callout | 10 | BD Mori | at the vaporiszer outlet.
18 | Callout | 11 | BD Mori | selected by Nitrogen Plant supplier within the the plant. The Nitrogen Plant supplier shall provide the necessary alarm,control and interlock to ensure that the export nitrogen temperature is always maintain above 60 degF.
19 | Callout | 12 | BD Mori | TTSJV shall review the nitrogen required for HUB1 with the comment in the above paragraph and revise as required.
20 | Callout | 12 | Abdul Rahim | in offsites and utilities
21 | Callout | 12 | BD Mori | or
22 | Callout | 12 | BD Mori | 5, 6, 7 SRUs, 3 , 4 TGTUs, 5, 6 SWSs and 2 or 3 ARU
23 | Callout | 14 | Abdul Rahim | All units feed tank will be on running gauge, but design should consider tank to tank transfer
24 | Callout | 14 | BD Mori | Refer bid technical query T493. TTSJV shall review and update this value and all the other values in this document as required.
25 | Callout | 15 | Abdul Rahim | All units feed tank will be on running gauge, but design should consider tank to tank transfer
26 | Callout | 16 | Abdul Rahim | All units feed tank will be on running gauge, but design should consider tank to tank transfer
27 | Callout | 17 | BD Mori | 5, 6, 7 SRUs, 3 , 4 TGTUs, 5, 6 SWSs
28 | Text Box | 18 | Abdul Rahim | All units feed tank will be on running gauge, but design should consider tank to tank transfer
29 | Callout | 20 | BD Mori | Add information on the plant turndown capacity after the Nitrogen Plant design is finalised.
30 | Callout | 22 | BD Mori | Total of a+b+c+d = 177380 lb/hr. Please check and update as required.
31 | Callout | 24 | BD Mori | This information in not applicable. Review and remove it. Refer the duty specification in MR for Nitrogen Plant.
32 | Callout | 24 | BD Mori | vppm
33 | Callout | 25 | BD Mori | the Nitrogen Plant vaporiser outlet.
34 | Callout | 25 | BD Mori | How nitrogen plant supplier will confirm this? This information shall be updated by TTSJV based on the detail engineering and necessary inputs from supplier
35 | Call-out | 26 | Mahdi Ali | Do not use FEED number
36 | Call-out | 27 | Mahdi Ali | Do not use FEED number
37 | Callout | 28 | BD Mori | Add block flow diagram as an attachment to this BOD. It shall not be a reference document for the BOD
38 | Call-out | 28 | Mahdi Ali | Do not use FEED number
39 | Call-out | 28 | Mahdi Ali | Remove 'h' from the unit number
40 | Call-out | 28 | Mahdi Ali | Drawing numbers not as per BMPS-A8