## CRS
Comment Resolution SHEET
|  |  | 098-F-DAT-00004-001 | Equipment Data Sheet for Reforming Furnace Burners
BAPCO Modernization Program
No. | Rev. | Page No. | BAPCO's comment | TTSJV(SOC)'s Response | Disc. | Open/Close | Remark (Or Attachment)
1 | AP | 1 | This Data Sheet has to be updated as result of FEED Validation and Detail design development. | Noted. | Engineering | Close |  | Jeung.Kim
2 | AP | 2 | please modify the name to : REFORMING FURNACE BURNERS | To be incorporated. | Engineering | Close |  | Salman Jaffer
3 | AP | 2 | 098F9800 | New tag number shall be updated. | Engineering | Close |  | Salman Jaffer
4 | AP | 3 | Please confirm is it 098F9800 or 098F9801 | New tag number shall be updated. | Engineering | Close |  | Salman Jaffer
5 | AP | 4 | sweet | To be incorporated. | Engineering | Close |  | Syed Ahmed
6 | AP | 5 | sweet | To be incorporated. | Engineering | Close |  | Syed Ahmed