## 310-A-PFD-00001-003-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | MAK | Always show the border size A1
2 | Cloud+ | 1 | Julio.Aguilar | Please, to be consistent with BMP process units modify the tittle as: SCALE CORROSION INHIBITOR DOSING PACKAGE"
3 | Cloud+ | 1 | Julio.Aguilar | Please, to be consistent with BMP process units modify the tittle as: SCALE CORROSION INHIBITOR DOSING PACKAGE"
4 | Callout | 1 | Julio.Aguilar | Prefix "u" to be removed
5 | Call-out | 1 | Mahdi Ali | Scale: NTS
6 | Text Box | 1 | Sameer.Ahmed | This drawing is given CODE-2 as a special case to allow TTSJV to proceed with development of subsequence deliverables and procurement activities. However, TTSJV shall be responsible to incorporate the comments and complete the design before finalizing the equipment PO. TTSJV to advise when the first utilities balance will be submitted for review. PFD shall be modified to incorporate the updated utilities streams data and H&M balance.
7 | Call-out | 1 | MAK | Total Sht. shall be indicated only, 004
8 | Text Box | 1 | MAK | Use the latest PFD border template that is part of Homogenization Procedure. SOC shall coordinate with JV Directorate.