## 358-S-DAT-80002-001-RAP
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout |  | BD Mori | This Long Lead Item (LLI) Material Requisition (MR) is being prepared by TTSJV based on the data available from FEED documents. As the detail engineering progresses, some of the information provided in this MR may change. TTSJV shall ensure that the changes arising from the detail engineering are fully incorporated in the MR before placing an order to the vendor. | Noted.
2 | Callout |  | Mohamed Ayyash | No. | Incorporated.
3 | Cloud+ |  | Ahmed Marhoon | "automatism" to be replaced to "automation" | Incorporated.
4 | Callout |  | Julio.Aguilar | Add space here | Incorporated.
5 | Text Box |  | Julio.Aguilar | to consider | Incorporated.
6 | Line |  | Julio.Aguilar |  | -
7 | Callout |  | Sameer.Ahmed | add "distillate" | Incorporated.
8 | Call-out |  | Ahmed Marhoon | Add a statement on the Automated Emergency Shutdown, if any, will be carried out by an independent ESD system. | Incorporated.
9 | Call-out |  | Ahmed Marhoon | Add a note on the Satellite Rack Rooms. | The comment is not clear. It shall be clarified by Client again.
10 | Call-out |  | Ahmed Marhoon | add: without violating environmental regulations. | Incorporated.
11 | Call-out |  | Ahmed Marhoon | Supplier to also verify the need for MCM. If needed, it shall be designed in compliance with BMPS-J15 | MCM will be provided by CONTRACTOR, not SUPPLIER.
12 | Call-out |  | Ahmed Marhoon | Alarms to be based on design an Hazop requirements. In any case, Alarm Objective Analysis to be carried out to finalize the list of alarms and their priorities. | This is material requisition for inquiry, alarm and trip should be finalized as per HAZOP result.
13 | Call-out |  | Ahmed Marhoon | Comments on section 3.2. of this document is also applicable to similar one of unit 356 and 357 within this Transmittal. | Noted.
14 | Callout |  | Mohamed Ayyash | N | Incorporated.
15 | Cloud+ |  | Julio.Aguilar | Replace ppm by ppmw | Incorporated.
16 | Cloud+ |  | Julio.Aguilar | Replace ppm by ppmw | Incorporated.
17 | Callout |  | Sameer.Ahmed | add "distillate" | Incorporated.
18 | Ellipse |  | Mohamed Ayyash |  | -
19 | Ellipse |  | Mohamed Ayyash |  | -
20 | Ellipse |  | Mohamed Ayyash |  | -
21 | Callout |  | Mohamed Ayyash | Use capital N | Incorporated.
22 | Arrow |  | Mohamed Ayyash |  | -
23 | Arrow |  | Mohamed Ayyash |  | -
24 | Arrow |  | Mohamed Ayyash |  | -
25 | Ellipse |  | Mohamed Ayyash |  | -
26 | Callout |  | Mohamed Ayyash | Use capital N | Incorporated.
27 | Ellipse |  | Mohamed Ayyash |  | -
28 | Arrow |  | Mohamed Ayyash |  | -
29 | Callout |  | Mohamed Ayyash | SCFM | Incorporated.
30 | Callout |  | Julio.Aguilar | Include (note 4) | It is not required because this datasheet is for only Desalination Package.
31 | Text Box |  | Julio.Aguilar | Add Note: (4) Feed to unit after Feed Strainer Package. | It is not required because this datasheet is for only Desalination Package.
32 | Ellipse |  | Mohamed Ayyash |  | -
33 | Callout |  | Mohamed Ayyash | Use capital N | Incorporated.
34 | Arrow |  | Mohamed Ayyash |  | -
35 | Arrow |  | Mohamed Ayyash |  | -
36 | Arrow |  | Mohamed Ayyash |  | -
37 | Callout |  | Saeed Taher | Trim material to be as per BMPS-L2 | Incorporated.
38 | Callout |  | Saeed Taher |  | -
39 | Cloud+ |  | Sameer.Ahmed | Drinking water | Incorporated.
40 | Callout |  | Mohamed Ayyash | Use capital N | Incorporated.
41 | Arrow |  | Mohamed Ayyash |  | -
42 | Ellipse |  | Mohamed Ayyash |  | -
43 | Arrow |  | Mohamed Ayyash |  | -