## 000-A-SCH-50003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Bernard.Grace | Quantities have changed from kick-off. There is a 800,000" dia reduction in piping. Confirm reason for reduction
2 | Callout | 2 | Nalini Mohan | Reference to WP1A for Sulphur Block to changed as per latest WBS
3 | Text Box | 3 | Omran A | General Comments: For all items related to DCS Systems for all WPs, add plant number
4 | Text Box | 5 | Erwin.Lugue | Missing activities for document approval of common documents for civil & structural basis of design to include: - Steelworks & foundations -Buildings -U/G -Piling design criteria ..etc.
5 | Callout | 7 | giovanny.rodriguez | general comment for L3 sch: LLI listed within basis of schedule (000-A-PLD-50002-001) shall be included
6 | Callout | 7 | Fernando.Perez | some times Silencer is placed in ASME Pumps Mat.requisition in Eq.List, check
7 | Callout | 7 | giovanny.rodriguez | general comment for L3 sch: trays are not included within equipment list.
8 | Callout | 8 | Fernando.Perez | some of this MR Number is mixed with ASME Pumps MR in Equipment List, this shall be updated in Eq.List
9 | Callout | 8 | giovanny.rodriguez | this package is unavailable within equipment list
10 | Text Box | 9 | Omran A | Does it cover HVAC Control System?
11 | Callout | 9 | giovanny.rodriguez | HVAC equipment list missing
12 | Callout | 16 | Erwin.Lugue | Early dates not updated especially for the geotechnical works
13 | Callout | 17 | Erwin.Lugue | These activities should be in the scope of procurement schedule not detailed engineering
14 | Call-out | 17 | CK Samy | Following for MOC shall be indicated separately Grounding and Lightning Protection Materials HV & LV Cables and Termination Kits Cable Glands Conduits and Accessories Electrical Cable Trays Welding Sockets and Receptacle Outlets Local Control Stations & Electrical Junction Boxes Lighting Material and Aircraft Warning Systems Electrical Monitoring & Control System (EmCS) Switchrack, Panel Boards & Dry Transformers LV Motors HV motors Cathodic Protection System heat tracing
15 | Text Box | 20 | Omran A | General Comment: Add plant/asset number for all instrumentation and Control Systems
16 | Text Box | 22 | Omran A | PEMS
17 | Text Box | 23 | Omran A | including Field instruments and Radar Gauges
18 | Text Box | 24 | Omran A | add (High Sensitivity Smoke Detector system)
19 | Callout | 26 | Fernando.Perez | some times Silencer is placed in ASME Pumps Mat.requisition in Eq.List, check
20 | Text Box | 34 | Omran A | The Following Process Systems are missing -Operator Training Simulator (OTS). -Cyber Security System. -CEMS (Continuous Emission Monitoring System) -Flow Computers if any.
21 | Text Box | 35 | Omran A | PEMS
22 | Text Box | 43 | Omran A | specify Tank No. Asset/Plant No.
23 | Text Box | 48 | Omran A | Loading arms control System is not reflected?
24 | Text Box | 53 | Omran A | Why most of the activities are not in chronological order? Schedule shall be developed per discipline
25 | Text Box | 53 | Omran A | and IFAT
26 | Text Box | 54 | Omran A | add IFAT if applicable
27 | Text Box | 54 | Omran A | General Comment: Specify plant/Asset No.
28 | Text Box | 54 | Omran A | Or MCM (Machine Condition Monitoring) System
29 | Text Box | 57 | Omran A | FAT on FO cables and issuing test certificates
30 | Text Box | 58 | Omran A | and CEMS (Continuous Emission Monitoring System)
31 | Callout | 78 | Fernando.Perez | Check, activities related to rotating equipments should be included in HCU / CDU / VDU / SGP
32 | Text Box | 99 | Omran A | This shall be done prior to placing PO for any Hardware or Software (i.e. prior to freezing/finalizing any software or hardware).
33 | Text Box | 99 | Omran A | General Comment: Why not in chronological order
34 | Text Box | 124 | Omran A | why not in chronological order for all activities?
35 | Callout | 139 | Erwin.Lugue | Check if activities includes the development of the overall piling layout & foundation plans
36 | Callout | 139 | Erwin.Lugue | Description of activity should refer to Bundwalls, Pit layout, Sections, & Details
37 | Text Box | 139 | Erwin.Lugue | General comments: - Delivery of drawings should accompany the calculation reports -Issuance of all the design deliverables should be tied to the schedule of the civil & structural basis of design document (BOD) approvals which are not mentioned in this schedule -Issuance of piled foundations & piles design criteria (common) -Update all buildings, & structures tagging in all the activities -Ensure that all the activities covers all the MOC scope, latest plot plans, & updated design deliverables list -Missing common activities for MTO -Missing common activities for civil siteworks -Missing constructability reviews -Missing preparation of tie-in plans & schedules (all units) -Missing schedule of model review schedule-30%, 60%, 90%
38 | Callout | 139 | Erwin.Lugue | Specify these activities -refers to which deliverables?
39 | Callout | 139 | Erwin.Lugue | Equipment structures are supposed to be steel. What are these RC structures in the description?
40 | Text Box | 139 | Erwin.Lugue | Issuance of MTO?
41 | Callout | 139 | Erwin.Lugue | Missing foundation plans & details for maintenance & access platforms, & shelters
42 | Text Box | 140 | Erwin.Lugue | Include overall composite U/G layout
43 | Callout | 140 | Erwin.Lugue | E& I trenches layout, & details
44 | Text Box | 140 | Erwin.Lugue | Issuance of MTO?
45 | Text Box | 140 | Erwin.Lugue | Missing overall interface plan drawings
46 | Callout | 140 | Erwin.Lugue | Breakdown of U/G systems layout, & details- OWS, CSS, etc.
47 | Callout | 140 | Erwin.Lugue | U/G systems layout, & details- OWS, CSS, etc.
48 | Callout | 140 | Erwin.Lugue | Check if activities includes the development of the overall piling layout & foundation plans
49 | Callout | 140 | Erwin.Lugue | Specify these activities- refers to which deliverables?
50 | Callout | 140 | Erwin.Lugue | Specify these activities- refers to which deliverables?
51 | Text Box | 140 | Erwin.Lugue | Missing plans for earthworks (cut & fill) drawings
52 | Callout | 140 | Erwin.Lugue | E& I Trenches Layout, Sections & Details
53 | Callout | 140 | Erwin.Lugue | Missing issuance of foundations for steel maintenance & access platforms, & shelters- IFR & IFC
54 | Text Box | 140 | Erwin.Lugue | Include overall composite U/G layout
55 | Callout | 140 | Erwin.Lugue | Paving & Grading plans
56 | Text Box | 140 | Erwin.Lugue | Issuance of MTO?
57 | Text Box | 140 | Erwin.Lugue | Missing plans for earthworks (cut & fill) drawings
58 | Text Box | 140 | Erwin.Lugue | Issuance of MTO?
59 | Text Box | 140 | Erwin.Lugue | Missing overall interface plan drawings
60 | Callout | 140 | Erwin.Lugue | Pit Layout, Sections, & Details
61 | Callout | 141 | Erwin.Lugue | Should these be foundations for access platforms, & shelters?
62 | Callout | 141 | Erwin.Lugue | Missing issuance for maintenance & access platforms, & shelters- IFR & IFC
63 | Text Box | 141 | Erwin.Lugue | Missing civil siteworks drawings
64 | Text Box | 141 | Erwin.Lugue | Missing overall interface plan drawings
65 | Text Box | 141 | Erwin.Lugue | Issuance of MTO?
66 | Text Box | 141 | Erwin.Lugue | Include overall composite U/G layout
67 | Callout | 141 | Erwin.Lugue | Breakdown of U/G Layout & Details- OWS, CSS, etc.
68 | Callout | 141 | Erwin.Lugue | Check if activities includes the development of the overall piling layout & foundation plans
69 | Callout | 141 | Erwin.Lugue | These refers to which deliverables?
70 | Text Box | 141 | Erwin.Lugue | Issuance of MTO?
71 | Text Box | 141 | Erwin.Lugue | Missing plans for earthworks (cut & fill) drawings
72 | Callout | 141 | Erwin.Lugue | Plans for tank farm Bundwalls, pit layout, sections, & details
73 | Text Box | 141 | Erwin.Lugue | Cooling tower structure & package units foundations?
74 | Text Box | 141 | Erwin.Lugue | Missing overall interface plan drawings
75 | Callout | 141 | Erwin.Lugue | Breakdown of U/G Layout & Details- OWS, CSS, etc.
76 | Text Box | 141 | Erwin.Lugue | Missing plans for earthworks (cut & fill) drawings
77 | Callout | 141 | Erwin.Lugue | Include the plans for new culverts
78 | Callout | 141 | Erwin.Lugue | Missing plans for foundations for maintenance & access platforms, & shelters
79 | Callout | 141 | Erwin.Lugue | E& I Trench Layout, Sections, & Details
80 | Callout | 141 | Erwin.Lugue | E& I Trench Layout, Sections, & Details
81 | Text Box | 141 | Erwin.Lugue | Include overall composite U/G layout
82 | Text Box | 141 | Erwin.Lugue | Issuance of MTO?
83 | Callout | 141 | Erwin.Lugue | Specify the structures- CW primary, & secondary basins, etc.
84 | Callout | 141 | Erwin.Lugue | Pit Layout, Sections, & Details
85 | Callout | 141 | Erwin.Lugue | Clarify activities-refers to which equipment structures deliverables?
86 | Text Box | 142 | Erwin.Lugue | Missing plans for earthworks (cut & fill) drawings
87 | Text Box | 142 | Erwin.Lugue | Issuance of MTO?
88 | Callout | 142 | Erwin.Lugue | Check if activities includes the development of the overall piling layout & foundation plans
89 | Text Box | 142 | Erwin.Lugue | Missing plans for civil siteworks drawings
90 | Text Box | 142 | Erwin.Lugue | Should include the backwater basins
91 | Text Box | 142 | Erwin.Lugue | Missing overall interface plan drawings
92 | Callout | 142 | Erwin.Lugue | E& I trench layout, & details
93 | Callout | 142 | Erwin.Lugue | Missing shelters for lube storage shelters
94 | Callout | 142 | Erwin.Lugue | Breakdown of U/G layout & details- OWS, CSS, etc.
95 | Callout | 142 | Erwin.Lugue | Pit Layout, sections, & details
96 | Callout | 142 | Erwin.Lugue | Specify activities- Refer to which deliverables?
97 | Text Box | 142 | Erwin.Lugue | Include overall composite U/G layout
98 | Text Box | 142 | Erwin.Lugue | Issuance of MTO?
99 | Callout | 143 | Erwin.Lugue | Specify activities- Refer to which deliverables?
100 | Text Box | 143 | Erwin.Lugue | Issuance of MTO?
101 | Callout | 143 | Erwin.Lugue | Should be under piperack structures? Specify activities- Refer to which deliverables?
102 | Callout | 143 | Erwin.Lugue | Missing shelters for lube storage shelters
103 | Callout | 143 | Erwin.Lugue | Missing shelters for lubes / chemical storage shelters
104 | Text Box | 143 | Erwin.Lugue | Issuance of MTO?
105 | Callout | 143 | Erwin.Lugue | Specify- Description refers to tanks platforms ? Access platforms?
106 | Callout | 143 | Erwin.Lugue | Should be under piperack structures? Specify activities- Refer to which deliverables?
107 | Callout | 143 | Erwin.Lugue | Should be under piperack structures? Specify activities- Refer to which deliverables?
108 | Text Box | 143 | Erwin.Lugue | Issuance of MTO?
109 | Text Box | 143 | Erwin.Lugue | Issuance of MTO?
110 | Callout | 143 | Erwin.Lugue | Missing shelters for lubes/ chemical storage shelters
111 | Callout | 144 | Fernando.Perez | some times Silencer is placed in ASME Pumps Mat.requisition in Eq.List, check
112 | Callout | 144 | giovanny.rodriguez | WPD trays - this code is not included at the equip list
113 | Callout | 144 | giovanny.rodriguez | WPD silencers - this code is not included at the equip list
114 | Callout | 144 | giovanny.rodriguez | WPD desuperheaters - this code is not included at the equip list
115 | Callout | 147 | giovanny.rodriguez | WPF trays - this code is not included at the equip list
116 | Callout | 149 | giovanny.rodriguez | WPJ silencer - this code is not included at the equip list
117 | Callout | 149 | giovanny.rodriguez | WPJ ASME pumps - this code is not included at the equip list
118 | Callout | 149 | giovanny.rodriguez | WPK silencers - this code is not included at the equip list
119 | Text Box | 150 | Berik.Nurbolatov | 2
120 | Text Box | 150 | Berik.Nurbolatov | 1
121 | Text Box | 150 | Berik.Nurbolatov | 3
122 | Text Box | 150 | Berik.Nurbolatov | 1.Please add activities on GENERAL ARRANGEMENT issues including the following revisions: IFI/IFD/IFC. 2.Heavy Lifting works scope should be added (Engineering/Construction phase:) Documentation/specification/plans to approve ( Engineering) Time calculation for heavy lifting activities on each Units ( Construction) 3.Mobilization data for Construction phase: Mobilization of Electro-Mechanical, Civil, electrical …..subcontractors. 4.Inspection activities shown be shown: Inspection of bulk materials, safety/fire equipment. The current schedule covers only Compressor inspection scope. 5.Piping Bulk material paragraph should be included, with the following data: Receive, Final Inspection, delivery at site. Material to follow as per above mentioned criteria’s: Seamless pipes, fittings( alloy, SS,CS..)gaskets, Valves, Steam traps, etc. 6.The issue of Isometrics for (IFI/IFR) are not shown. As per the schedule , Isometrics comes with IFC. The for IFI/IFC should advised. 7.The issue of plot plan for IDD should be finalized by 30% model review. Plot plan will be used as a guides. All allocation /layout modification should be completed by the time of 30% review. 8.The list of abbreviations would be grateful to attach for reference. 9.Please mind the Piping erection activity in regards to Piping Support Erection. Sheet 174.WP E HCU -Piping Supports erection finishes (29 Nov 20) after Piping erection on Racks ( 16 Sept 20) 10.Piping Erection as well as piping testing duration is believed /assumed to be VERY approximate as the time dedicated for the mentioned activities on the Units: SGP, Tank Farm and Cooling Tower is similar. However, Units equipment’s number, piping bulk material scope and structure scopes vary. Please advise. Page 175.
123 | Callout | 150 | Berik.Nurbolatov | All OCs activities scope should be given in one set format and sections should be named in unique manner.
124 | Callout | 150 | Berik.Nurbolatov | EPC to check the scheduled time b/n 30% and 60% model review as per scope volume of to cover on 60% review.
125 | Callout | 150 | Berik.Nurbolatov | The deliverable item should shifted to piping support paragraph,if required such should be set.
126 | Callout | 150 | Berik.Nurbolatov | The sequence should be updated
127 | Callout | 151 | Berik.Nurbolatov | The deliverable item should shifted to piping support paragraph,if required such should be set.
128 | Callout | 151 | Berik.Nurbolatov | All the highlighted items should be withdrawn from F&G paragraph, and located in Overall piping activities.
129 | Call-out | 155 | CK Samy | Following data sheets/ITPS for each MOC units shall be submitted Electrical Monitoring & Control System (EmCS) Switchrack, Panel Boards & Dry Transformers Power / Distribution Transformers and Neutral Grounding Resistors HV Switchgears HV & LV Bus Duct LV Switchgears MV & LV Power Capacitor Banks AC & Dc UPS Systems LV Motors HV motors Cathodic Protection System Emergency Diesel Generators heat tracing
130 | Text Box | 170 | Erwin.Lugue | Geotechnical investigations & recommendations?
131 | Text Box | 170 | Erwin.Lugue | Missing issuance of building overall site development plan
132 | Text Box | 170 | Erwin.Lugue | Interface plans for U/G & roads/paving?
133 | Text Box | 170 | Erwin.Lugue | Generator & transformer pads & steelworks?
134 | Callout | 170 | Erwin.Lugue | Piling Plans?
135 | Text Box | 170 | Erwin.Lugue | Geotechnical investigations & recommendations?
136 | Text Box | 170 | Erwin.Lugue | Issuance of MTO?
137 | Text Box | 170 | Erwin.Lugue | Missing issuance of building overall site development plan
138 | Callout | 170 | Erwin.Lugue | Piling Plans?
139 | Text Box | 170 | Erwin.Lugue | Geotechnical investigations & recommendations?
140 | Callout | 170 | Erwin.Lugue | Missing issuance of Building Plumbing, & Drainage plans?
141 | Text Box | 170 | Erwin.Lugue | Issuance of MTO?
142 | Text Box | 170 | Erwin.Lugue | Missing issuance of building overall site development plan
143 | Callout | 170 | Erwin.Lugue | Missing issuance of Building Plumbing, & Drainage plans?
144 | Text Box | 170 | Erwin.Lugue | Generator & transformer pads & steelworks?
145 | Text Box | 170 | Erwin.Lugue | Interface plans for U/G & roads/paving?
146 | Callout | 170 | Erwin.Lugue | Piling Plans?
147 | Text Box | 170 | Erwin.Lugue | Generator & transformer pads & steelworks?
148 | Callout | 170 | Erwin.Lugue | Missing issuance of Building Plumbing, & Drainage plans?
149 | Text Box | 170 | Erwin.Lugue | Interface plans for U/G & roads/paving?
150 | Text Box | 170 | Erwin.Lugue | Issuance of MTO?
151 | Callout | 185 | Nalini Mohan | List the activities as per the chronological order. Here IDD2 (Jan 19) is shown on top while IBD (June 18) is shown on bottom. This is a typical observation and applies to entire SOC portion.
152 | Callout | 185 | Nalini Mohan | Add separate activities for N2 Plant as it is a completely separate entity
153 | Callout | 189 | Nalini Mohan | Major U/G Layout with gravity piping should be made available for 30% model review. 30% model review is scheduled around 16th Aug. Accordingly, rework timing of U/G Piping layout (currently shown as 5Nov-S, 31Dec-F)