## 000-B-MST-50003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | scott.hillman | Document to be reissued for Approval once Sub-contractor and fabrication companies have been appointed and their procedures have been incorporated.
2 | Text Box | 1 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
3 | Text Box | 1 | Mahdi Ali | THIS DOCUMENT IS A SPECIFICATIN AND NOT A METHOD STATEMENT AS PER THE TITLE. THUS THE DOCUMENT TYPE SHALL BE 'TSP' AND NOT 'MST'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS IS A METHOD STATEMENT THEN THE TITLE OF THIS DOCUMENT SHOULD CHANGE ACCORDINGLY.
4 | Callout | 4 | Yousif Ahmadi | Delete
5 | Callout | 4 | Yousif Ahmadi | Jon construction specification for welders management
6 | Callout | 4 | Yousif Ahmadi | This specification to be correlated with .....
7 | Callout | 8 | Yousif Ahmadi | Who shall do this tack welding?
8 | Callout | 12 | Yousif Ahmadi | 100%
9 | Callout | 13 | Yousif Ahmadi | Nb
10 | Callout | 13 | Yousif Ahmadi | The rages per ASME II (A) and II (C) are different than below two tables. Please explain the basis of these ranges