## 000-C-MRQ-60002-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | REVIEW AND ADDRESS THESE COMMENTS WHERE APPLICABLE
2 | Text Box | 1 | Danut.Dragan | DS GENERAL COMMENTS: 1. Level Instruments - the H or HH levels cannot coincide with the Max of any Level Range. Similarly for L or LL at Min Range. 2. Level Instruments Drawing - - Nozzles shall be marked on the drawing as noted in the Nozzle Schedule (i.e. N5 A) - Correct number and Elevation / Orientation of Nozzles, relevant dimensions and angles shall be represented - The Liquid Level Limits: "LL", "L", "H", "HH" marks shall be followed by the Elevation figure relative to TTL. 3. Nozzle schedule: - nozzles for Level Instruments should be represented consistently: i.e. "N5 A" and "N5 B" or "N5 A-B" or "N5 A/B". - Service description shall be "Level Instrument" - Process Connection shall be as per the respective P&ID, type of flange (specify Grayloc and Seal type if applicable), rating, seal. 4. Note 7 in this DS, or similar in all others: "The measuring range of all Level Measurement Instruments shall be the same.". To be completed with: "... for the same service.".
3 | Callout | 1 | Fatema Hashem | GENERAL COMMENT: PLEASE NOTE THAT OWNER COMMENTS PROVIDED ON BMP-ROC-TRI-00137 HAVE NOT BEEN ADDRESSED ON THE DATASHEETS ATTACHED TO THIS MR
4 | Text Box | 1 | Danut.Dragan | GAD GENERAL COMMENTS: 1. Where Process Connection Size and type is not known / decided, mention: VTA and "ON HOLD" "INSTR.-NUCLEAR SOURCE WELL" for clarity. 2. Wherever the Skin Thermo-couples are not visible on the skirt of the vessel, they shall be mentioned in a Note. 3. Hight of the Level Instrument Nozzles to be checked and confirmed correct. "Detector" should be replaced by "Transmitter" for AIT and LIT Nozzles. 4. Process Connection for Nuclear Transmitters, are four "legs" for each mounting Pad. Anyway, details shall be decided by Instrument Vendor / Vessel Vendor Engineering, shall be noted - VTA / ON HOLD. 5. Nuclear Transmitters and skin Thermocouple - Process connections are not intrusive and might be represented with a separate symbol, not as a Nozzle.
5 | Cloud+ | 1 | MAK | Refer to page 2/2
6 | Cloud+ | 3 | MAK | Change in all pages to Bapco Doc. No.
7 | Callout | 7 | Fatema Hashem | INCLUDE LICENSOR SPECIFICATIONS PVM-SU-5004H AND CPM-SU-5012B
8 | Call-out | 7 | Ali Kadhem | As per the GAD drawing for 021V0015 i.e. referenced drawings, please include “UOP Standard Drawing for Vortex Breakers 3-22”.
9 | Call-out | 17 | Rashed Almudahka | There is no order of precedence within the technical documents per Annex 1 of the contract
10 | Text Box | 37 | Rashed Almudahka | include BMPS-M6 to the reference list
11 | Call-out | 41 | Rashed Almudahka | as per BMPS-N1, insulation thickness shall be 50mm. please clarify
12 | Text Box | 45 | Rashed Almudahka | include BMPS-M6 to the reference list
13 | Call-out | 45 | Rashed Almudahka | BMPS-N1 to be checked.
14 | Call-out | 48 | Rashed Almudahka | vessel to be completely heat treated
15 | Text Box | 53 | Rashed Almudahka | include BMPS-M6 to the reference list
16 | Call-out | 56 | Rashed Almudahka | Vessel to be completely PWH treated
17 | Call-out | 65 | Rashed Almudahka | vessel to be completely PWH treated
18 | Text Box | 73 | rob.urban | catalyst slurry
19 | Callout | 74 | Fatema Hashem | ENSURE THESE SPECIFICATIONS ARE INCLUDED IN THE MR
20 | Call-out | 74 | Rashed Almudahka | Seismic zone (0) to be marked.
21 | Text Box | 76 | asantilli | 1.6 mm
22 | Text Box | 76 | asantilli | 018V0037/018V0038
23 | Text Box | 76 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 5 of 26
24 | Text Box | 76 | asantilli | 6.4
25 | Text Box | 76 | asantilli | 1.6 mm
26 | Text Box | 77 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 6 of 26
27 | Text Box | 77 | asantilli | 018V0037/018V0038
28 | Text Box | 78 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 7 of 26
29 | Text Box | 78 | asantilli | 018V0037/018V0038
30 | Text Box | 79 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 8 of 26
31 | Text Box | 79 | asantilli | (018V0037/0038)
32 | Text Box | 80 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 9 of 26
33 | Text Box | 80 | asantilli | (018V0037/0038)
34 | Text Box | 81 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 10 of 26
35 | Text Box | 81 | asantilli | (018V0037/0038)
36 | Text Box | 81 | asantilli | (018V0037&0038)
37 | Text Box | 82 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 11 of 26
38 | Text Box | 82 | asantilli | (018V0037/0038)
39 | Text Box | 83 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 12 of 26
40 | Text Box | 83 | asantilli | (018V0037/0038)
41 | Text Box | 84 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 13 of 26
42 | Text Box | 84 | asantilli | (018V0037/0038)
43 | Text Box | 84 | asantilli | (018V0037 & 018V0038)
44 | Text Box | 85 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 14 of 26
45 | Text Box | 85 | asantilli | (018V0037/0038)
46 | Text Box | 86 | asantilli | (018V0037/0038)
47 | Text Box | 86 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 15 of 26
48 | Text Box | 87 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 16 of 26
49 | Text Box | 87 | asantilli | (018V0037/0038)
50 | Text Box | 88 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 17 of 26
51 | Text Box | 88 | asantilli | (018V0037/0038)
52 | Text Box | 89 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 18 of 26
53 | Text Box | 89 | asantilli | (018V0037/0038)
54 | Text Box | 90 | asantilli | 018V0037
55 | Text Box | 90 | asantilli | 018V0037
56 | Text Box | 90 | asantilli | 018V0038
57 | Text Box | 90 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 19 of 26
58 | Text Box | 90 | asantilli | (018V0037/0038)
59 | Text Box | 90 | asantilli | 018V0037
60 | Text Box | 90 | asantilli | 018V0037
61 | Text Box | 90 | asantilli | 018V0038
62 | Text Box | 91 | asantilli | 018V0038
63 | Text Box | 91 | asantilli | 018V0038
64 | Text Box | 91 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 20 of 26
65 | Text Box | 91 | asantilli | 018V0037
66 | Text Box | 91 | asantilli | 018V0038
67 | Text Box | 91 | asantilli | (018V0037/0038)
68 | Text Box | 92 | asantilli | 018V0038
69 | Text Box | 92 | asantilli | 018V0037
70 | Text Box | 92 | asantilli | 018V0037
71 | Text Box | 92 | asantilli | 018V0038
72 | Text Box | 92 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 21 of 26
73 | Text Box | 92 | asantilli | 018V0037
74 | Text Box | 92 | asantilli | (018V0037/0038)
75 | Text Box | 92 | asantilli | 018V0038
76 | Text Box | 92 | asantilli | 018V0037
77 | Text Box | 92 | asantilli | 018V0038
78 | Text Box | 93 | asantilli | (018V0037/0038)
79 | Text Box | 93 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 22 of 26
80 | Text Box | 94 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 23 of 26
81 | Text Box | 94 | asantilli | (018V0037/0038)
82 | Text Box | 95 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 24 of 26
83 | Text Box | 95 | asantilli | (018V0037/0038)
84 | Text Box | 96 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 25 of 26
85 | Text Box | 96 | asantilli | (018V0037/0038)
86 | Text Box | 97 | gmariano | Doc.018-C-DAT-00004-001 Rev. A Sh. 26 of 26
87 | Text Box | 97 | asantilli | (018V0037/0038)
88 | Text Box | 99 | Rashed Almudahka | include BMPS-M6 in the reference list
89 | Text Box | 101 | Rashed Almudahka | refer to OWNER comment on 018V0037 data sheet
90 | Text Box | 102 | rob.urban | catalyst slurry
91 | Text Box | 105 | asantilli | 1.6 mm
92 | Text Box | 105 | asantilli | 018V0037/018V0038
93 | Text Box | 105 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 5 of 26
94 | Text Box | 105 | asantilli | 6.4
95 | Text Box | 105 | asantilli | 1.6 mm
96 | Text Box | 106 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 6 of 26
97 | Text Box | 106 | asantilli | 018V0037/018V0038
98 | Text Box | 107 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 7 of 26
99 | Text Box | 107 | asantilli | 018V0037/018V0038
100 | Text Box | 108 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 8 of 26
101 | Text Box | 108 | asantilli | (018V0037/0038)
102 | Text Box | 109 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 9 of 26
103 | Text Box | 109 | asantilli | (018V0037/0038)
104 | Text Box | 110 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 10 of 26
105 | Text Box | 110 | asantilli | (018V0037/0038)
106 | Text Box | 110 | asantilli | (018V0037&0038)
107 | Text Box | 111 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 11 of 26
108 | Text Box | 111 | asantilli | (018V0037/0038)
109 | Text Box | 112 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 12 of 26
110 | Text Box | 112 | asantilli | (018V0037/0038)
111 | Text Box | 113 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 13 of 26
112 | Text Box | 113 | asantilli | (018V0037/0038)
113 | Text Box | 113 | asantilli | (018V0037 & 018V0038)
114 | Text Box | 114 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 14 of 26
115 | Text Box | 114 | asantilli | (018V0037/0038)
116 | Text Box | 115 | asantilli | (018V0037/0038)
117 | Text Box | 115 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 15 of 26
118 | Text Box | 116 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 16 of 26
119 | Text Box | 116 | asantilli | (018V0037/0038)
120 | Text Box | 117 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 17 of 26
121 | Text Box | 117 | asantilli | (018V0037/0038)
122 | Text Box | 118 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 18 of 26
123 | Text Box | 118 | asantilli | (018V0037/0038)
124 | Text Box | 119 | asantilli | 018V0037
125 | Text Box | 119 | asantilli | 018V0037
126 | Text Box | 119 | asantilli | 018V0038
127 | Text Box | 119 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 19 of 26
128 | Text Box | 119 | asantilli | (018V0037/0038)
129 | Text Box | 119 | asantilli | 018V0037
130 | Text Box | 119 | asantilli | 018V0037
131 | Text Box | 119 | asantilli | 018V0038
132 | Text Box | 120 | asantilli | 018V0038
133 | Text Box | 120 | asantilli | 018V0038
134 | Text Box | 120 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 20 of 26
135 | Text Box | 120 | asantilli | 018V0037
136 | Text Box | 120 | asantilli | 018V0038
137 | Text Box | 120 | asantilli | (018V0037/0038)
138 | Text Box | 121 | asantilli | 018V0038
139 | Text Box | 121 | asantilli | 018V0037
140 | Text Box | 121 | asantilli | 018V0037
141 | Text Box | 121 | asantilli | 018V0038
142 | Text Box | 121 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 21 of 26
143 | Text Box | 121 | asantilli | 018V0037
144 | Text Box | 121 | asantilli | (018V0037/0038)
145 | Text Box | 121 | asantilli | 018V0038
146 | Text Box | 121 | asantilli | 018V0037
147 | Text Box | 121 | asantilli | 018V0038
148 | Text Box | 122 | asantilli | (018V0037/0038)
149 | Text Box | 122 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 22 of 26
150 | Text Box | 123 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 23 of 26
151 | Text Box | 123 | asantilli | (018V0037/0038)
152 | Text Box | 124 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 24 of 26
153 | Text Box | 124 | asantilli | (018V0037/0038)
154 | Text Box | 125 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 25 of 26
155 | Text Box | 125 | asantilli | (018V0037/0038)
156 | Text Box | 126 | gmariano | Doc.018-C-DAT-00005-001 Rev. A Sh. 26 of 26
157 | Text Box | 126 | asantilli | (018V0037/0038)
158 | Call-out | 132 | Rashed Almudahka | TYPICAL COMMENT Seismic zone (0) to be marked
159 | Call-out | 155 | Rashed Almudahka | RTJ
160 | Text Box | 159 | Rashed Almudahka | TYPICAL COMMENT include BMPS-M6 to the reference list where applicable.
161 | Callout | 181 | Fatema Hashem | ENSURE THIS SPECIFICATION IS INCLUDED IN THE MR
162 | Callout | 181 | Fatema Hashem | ENSURE THIS SPECIFICATION IS INCLUDED IN THE MR
163 | Text Box | 205 | Ali Kadhem | Our comment provided in in the datasheet of 021V0003 issued in the Transmittal BMP-ROC-TRI-00141 has not been incorporated and need to be addressed. For your ready reference the comment is: "As per EDP drawing , Note 2: “For temperature and pressure curves see subsheets immediately following this vessel sheet”, i.e. sheets 992381-301-9A/9B/9C. Please check and include."
164 | Call-out | 208 | Rashed Almudahka | TYPICAL COMMENT As agreed earlier, weight and loading data to be removed from the data sheet and plotted in the mechanical drawing only.
165 | Call-out | 211 | Ali Kadhem | Our comment provided in the GAD of 021V0003 issued in the Transmittal BMP-ROC-TRI-00139 has not been incorporated and need to be addressed. For your ready reference the comment is: "As per EDP drawing, T.L TO T.L is 16’ 6” which is also approximately 5030 mm. Please check and confirm."
166 | Call-out | 218 | Rashed Almudahka | check and confirm bolting material
167 | Call-out | 219 | Ali Kadhem | As per the vessel datasheet, "Vessel to be designed and fabricated in accordance with UOP Standard Specification 3-12." To be included.
168 | Call-out | 220 | Ali Kadhem | Our comment provided in the GAD of 021V0004 issued in the Transmittal BMP-ROC-TRI-00139 has not been incorporated and need to be addressed. For your ready reference the comment is: "(RAISED) - As per EDP drawing (992381-301 Sheet 11)."
169 | Call-out | 231 | Rashed Almudahka | vessel to be PWH treated as well
170 | Call-out | 238 | Ali Kadhem | Our comment provided in the GAD of 021V0009 issued in the Transmittal BMP-ROC-TRI-00139 has not been incorporated and need to be addressed. For your ready reference the comment is: "(RAISED) - As per EDP drawing (992381-301 Sheet 12)"
171 | Call-out | 240 | Rashed Almudahka | vessel to be fully PWH treated as well
172 | Call-out | 249 | Rashed Almudahka | vessel to be under full RT requirement
173 | Call-out | 250 | Rashed Almudahka | internal cladding to be checked
174 | Call-out | 254 | Rashed Almudahka | full RT is required