## 000-C-MRQ-60010-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | 2018-01-02
2 | Cloud+ | 1 | MAK | Refer to page 2/2
3 | Call-out | 4 | Ali Kadhem | For 3HDU (021) vessels (021V0002 and 021V0023), please refer to Owner’s comments provided in the Rev.A of the datasheets in the transmittal BMP-ROC-TRI-00356.
4 | Callout | 4 | Fatema Hashem | REFER TO OWNER COMMENTS MADE ON REV A DATASHEETS AND DRAWINGS: BMP-ROC-TRI-00350, BMP-ROC-TRI-00363 and BMP-ROC-TRI-00380
5 | Text Box | 4 | Ahmed Bucheeri | Refer to owner comments in all data sheets and drawings of all vessels
6 | Call-out | 5 | Ali Kadhem | For 3HDU (021) vessels (021V0002 and 021V0023), please refer to Owner’s comments provided in the Rev.A of the mechanical drawings in the transmittals BMP-ROC-TRI-00364 and BMP-ROC-TRI-00372, respectively.
7 | Text Box | 5 | Mahdi Ali | S
8 | Text Box | 5 | Mahdi Ali | S
9 | Callout | 12 | David.Jimenez | Excessive time frame. Typically 1 week or 2 weeks maximum. In addition cannot be same date as A2001, but prior to that date
10 | Callout | 12 | David.Jimenez | How can GADs be validated if calculation notes are not yet delivered
11 | Callout | 21 | Danut.Dragan | Nuclear Detectors, Level or Density: - Welded Bosses for Plate supporting shall be specified and preliminary documented. For execution, Nuclear Instrument Vendor To Advise.
12 | Text Box | 29 | Ahmed Bucheeri | PMI H W W R
13 | Text Box | 32 | David.Jimenez | These values refer to operating conditions and should be provided (Typ. comment)
14 | Callout | 42 | Danut.Dragan | nuclear sources (for Density Detectors)
15 | Callout | 42 | Danut.Dragan | Nozzle tags to be shown
16 | Callout | 43 | Danut.Dragan | Nuclear source for Density Detectors
17 | Callout | 44 | Danut.Dragan | Nuclear sources for Density Detectors
18 | Callout | 44 | Danut.Dragan | Density
19 | Callout | 45 | Danut.Dragan | Nuclear sources for Density Detectors
20 | Callout | 50 | Danut.Dragan | add "... for the same range"
21 | Callout | 51 | Danut.Dragan | Hight dimensions to be provided
22 | Callout | 51 | Danut.Dragan | All nuclear instruments will be installed on special supporting pads
23 | Callout | 51 | Danut.Dragan | no level defined for this nozzle
24 | Callout | 51 | Danut.Dragan | All Nozzles to be Tagged as in Nozzle Schedule
25 | Callout | 53 | Danut.Dragan | Nuclear Sources for Nuclear Level and Density Instruments
26 | Callout | 53 | Danut.Dragan | Nozzles: one Density Analyser, one Level Switch, and two Level Transmitters. All Nuclear
27 | Callout | 53 | Danut.Dragan | These nozzles shall be marked / tagged with separate nos, as they represent four different Instruments, one Density Analyser, one Level Point Switch, and two Level Transmitters.
28 | Callout | 53 | Danut.Dragan | there is no Level Definition for N12C
29 | Callout | 55 | Danut.Dragan | These nozzles shall be marked / tagged with separate nos, as they represent four different Instruments, one Density Analyser, one Level Point Switch, and two Level Transmitters.
30 | Callout | 55 | Danut.Dragan | there is no Level Definition for N12C
31 | Callout | 56 | Danut.Dragan | Same comments as for 018V0033
32 | Callout | 64 | Danut.Dragan | Same comments as for 018V0033
33 | Callout | 72 | Danut.Dragan | Same comments as for 018V0033
34 | Callout | 83 | Danut.Dragan | Relative Hight of Nozzles to be specified.
35 | Callout | 83 | Danut.Dragan | in P&ID it looks located on the vessel's shell, not on the top. Contractor to confirm.
36 | Callout | 84 | Danut.Dragan | "for the same range"
37 | Callout | 87 | Danut.Dragan | in P&ID it looks located on the vessel's shell, not on the top. Contractor to confirm.
38 | Callout | 87 | Danut.Dragan | Nozzles position shall be dimensioned.
39 | Callout | 91 | Danut.Dragan | Nozzles position shall be dimensioned. - Nozzle Tags to be provided in drawing - A pair of Nozzles is missing
40 | Callout | 92 | Danut.Dragan | "for the same ranges"
41 | Callout | 96 | Danut.Dragan | Same comments as for 018V2008