## 000-C-MRQ-60012-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Mahdi Ali | shall be 001 to 003
2 | Call-out | 4 | Ali Kadhem | As per EDP Columns/vessels specification sheets, please include the following UOP standards: 3-115, 3-122, 3-264, 3-392 and ensure all the licensor (UOP) specifications and standard drawings are included.
3 | Callout | 4 | Fatema Hashem | INCLUDE CLG STANDARD DRAWNG RB-910354
4 | Text Box | 11 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
5 | Call-out | 13 | Rashed Almudahka | There is no order of precedence within the technical documents per Annex 1 of the contract.
6 | Callout | 13 | Fatema Hashem | THIS SUPPLY IS NOT FOR LARGE COLUMNS. THIS IS A COPY/PASTE FROM ATMOSPHERIC AND VAC COLUMNS INTERNALS MR. CORRECT REFERENCES IN ALL OF THIS DOCUMENT
7 | Call-out | 15 | Rashed Almudahka | Include the vendors as per OWNER AVL in the sub supplier list.
8 | Text Box | 24 | Omran A | loaded with perpetual application software and also comply with BMPS-J40