## 000-C-MST-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | steven.coyne | This document is close to being code 4, please can you IDC or SC prior to Owner review.
2 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A SPECIFICATIN AND NOT A METHOD STATEMENT. THUS THE DOCUMENT TYPE SHALL BE 'TSP' AND NOT 'MST'. CHANGE THE DOCUMENT NUMBER AND CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A METHOD STATEMENT THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY
3 | Callout | 1 | Mahdi Ali | DELETE 'OVERALL'
4 | Text Box | 2 | giovanny.rodriguez | 10
5 | Text Box | 2 | giovanny.rodriguez | 9. PAINT / INSULATION REPARATION
6 | Cloud+ | 2 | MAK | Page numbers missing? Why we are receiving different formats of document indexes?
7 | Cloud+ | 3 | MAK | Bapco Doc. No.
8 | Text Box | 3 | giovanny.rodriguez | Below listed are BMPS/JV documentation that should also be followed: BMPS-B5 COATING OF EXTERNAL SURFACES AND COLOUR CODING BMPS-B10 FIELD INSPECTION REQUIREMENTS BMPS-N1 INSULATION BMPS-B-50054 TYPICAL MECHANICAL QC FORMS FOR PRE-COMMISSIONING AND COMMISSIONING BMPS-B-50061 TYPICAL CIVIL QC FORMS FOR INSTALLATION BMPS-B-50064 TYPICAL PAINTING & INSULATION QC FORMS FOR INSTALLATION BMPS-B-50067 TYPICAL STEEL STRUCTURE QC FORMS FOR INSTALLATION BMPS-B-50069 TYPICAL MECHANICAL QC FORMS FOR INSTALLATION BMPS-C-50116 STANDARD DRAWING SUPPORT SADDLES FOR HORIZONTAL PRESSURE VESSELS AND SHELL AND TUBE HEAT EXCHANGERS BMPS-C-50101 STANDARD DRAWING SUPPORT SADDLES FOR STACKED UNIT 076551C-000D-STC-1790-001-001/000-Q-STD-50001-001 CONCRETE WORKS EMBEDDED PLATES TYPICAL DETAILS 076551C-000D-STC-1790-002-001/000-Q-STD-50002-001 CONCRETE WORKS SLIDING PLATES TYPICAL DETAILS
9 | Text Box | 4 | giovanny.rodriguez | ADD: VENDOR/MANUFACTURER
10 | Text Box | 4 | giovanny.rodriguez | 6.1.4. Manual & electrical tools, power/special tools, electrical generators, movable lights, scaffolding, blower & fans, pluged ends electrical wires/cables, welding machine, consumables, loose/structural material, etc., as well as any related material, equipment, procedure/specification (installation, welding, surface preparation, cleaning, among to others) shall be available prior to initiate any installation work.
11 | Call-out | 4 | RASHED SHOWAITER | RIGGING STUDY TO BE ISSUED
12 | Text Box | 4 | giovanny.rodriguez | FOR INSTALLATION ACTIVITIES RELATED TO STATIC EQUIPMENTS AND/OR TRAYS/INTERNALS ??
13 | Cloud+ | 4 | MAK | Provide Bapco Doc. No.
14 | Text Box | 4 | giovanny.rodriguez | OWNER
15 | Cloud+ | 4 | MAK | Provide Bapco Doc. No.
16 | Callout | 4 | giovanny.rodriguez | "AS BUILT"
17 | Text Box | 4 | giovanny.rodriguez | and cross checked with packing list for its acceptance. Any discrepancy or anomaly/damage shall be immediatly notified to the CONTRACTOR warehouse keeper & to OWNER inspection body.
18 | Text Box | 4 | giovanny.rodriguez | ADD: and according to vendor / MFR recomendations
19 | Text Box | 5 | giovanny.rodriguez | Adequate form from BMPS-B-50061 TYPICAL CIVIL QC FORMS FOR INSTALLATION shall be fulfiled for any inherent installation activity.
20 | Call-out | 5 | RASHED SHOWAITER | LIGHTING ARRANGEMENT AND STUDY THE RISK AND SAFETY OF HEAVY LIFTING AT NIGHT.
21 | Text Box | 5 | Aamer.Hubail | lifting gears
22 | Text Box | 6 | giovanny.rodriguez | Adequate form from BMPS-B-50069 TYPICAL MECHANICAL QC FORMS FOR INSTALLATION shall be fulfiled for any inherent installation activity.
23 | Text Box | 6 | giovanny.rodriguez | ADD: Special care should be taken for stacked heat exchanger, as the top saddles shall be adequate fixed to the support at the lower heat exchanger, and the process nozzles between HX at shell and tube sides shall be connected using flanges and adequate gaskets/studs or welded as applicable.
24 | Text Box | 7 | giovanny.rodriguez | missing
25 | Text Box | 7 | giovanny.rodriguez | vessels pad/lug.
26 | Callout | 7 | giovanny.rodriguez | and those
27 | Text Box | 7 | giovanny.rodriguez | Adequate form from BMPS-B-50067 TYPICAL STEEL STRUCTURE QC FORMS FOR INSTALLATION & BMPS-B-50061 TYPICAL CIVIL QC FORMS FOR INSTALLATION shall be fulfiled for any inherent installation activity.
28 | Text Box | 7 | giovanny.rodriguez | REPLACE 7.3.2: Special precaution should be taken to avoid any weld arc with vessel internal/external walls. (Welding or burning to the vessel walls is forbidden).
29 | Text Box | 7 | giovanny.rodriguez | Adequate form from BMPS-B-50067 TYPICAL STEEL STRUCTURE QC FORMS FOR INSTALLATION shall be fulfiled for any inherent installation activity.
30 | Text Box | 8 | giovanny.rodriguez | REPLACE 8.1.14: Special precaution should be taken to avoid any weld arc with vessel internal/external walls. (Welding or burning to the vessel walls is forbidden).
31 | Call-out | 8 | RASHED SHOWAITER | ENSURE CLEANING BOTTOM HEAD AFTER REMOVAL OF SCAFFOLDING.
32 | Text Box | 8 | giovanny.rodriguez | IDEM TO OR REFER TO: 7.4.3/7.4.4
33 | Callout | 8 | giovanny.rodriguez | neither permanently deformed
34 | Text Box | 8 | giovanny.rodriguez | CHECK for the tightening of bolts & clamps.
35 | Call-out | 8 | RASHED SHOWAITER | AND NO FORGOTTEN TOOLS OR PPE
36 | Text Box | 8 | giovanny.rodriguez | CHECK for the tightening of bolts & clamps.
37 | Text Box | 8 | giovanny.rodriguez | shall not be
38 | Text Box | 8 | giovanny.rodriguez | Prior to initiate any installation, CHECK that all pieces/parts/bolting/clamps are available and their quantities are in accordance with packing list and MFR installation manuals.
39 | Call-out | 8 | RASHED SHOWAITER | ENSURE INSPECTION AND CLEANING CONDITION OF TRAYS
40 | Call-out | 8 | RASHED SHOWAITER | PROVIDE EXTRA BOLTS AND NUTS FOR TRAYS SEGMENTS AND M/W AS MANY WILL BREAK.
41 | Text Box | 8 | giovanny.rodriguez | In any case, CHECK for the correct trays/internals installation sequence in accordance to MFR installation manuals.
42 | Call-out | 8 | RASHED SHOWAITER | TO BE INSTALLED UNDER THE SUPERVISION OF A REPRESENTATIVE FROM THE MFR. UPON INSTALLATION, ACCEPTANCE TO BE SIGNED BY THE REPRESENTATIVE.
43 | Text Box | 10 | giovanny.rodriguez | 10. 10.1
44 | Cloud+ | 10 | MAK | Provide Bapco Doc. No.
45 | Text Box | 10 | giovanny.rodriguez | 9. PAINT / INSULATION REPARATION 9.1 Paint Reparations After equipments, platforms and trays/internals installation, CONTRACTOR shall verify that any paint damage should be repaired as applicable in accordance with BMPS-B5 8.13; in any case, the adecuate/selected paint system according to BMPS-B5 shall be re-applied to that repaired area. Any paint reparation shall be also reported using the PAINTING SUMMARY REPORT from BMPS-B-50064 TYPICAL PAINTING & INSULATION QC FORMS FOR INSTALLATION. 9.2 Insulation Reparations After equipments, platforms and trays/internals installation, CONTRACTOR shall verify that any insulation damage should be repaired as applicable in accordance with BMPS-N1 5.4 & 15.0; in any case, the adecuate/selected insulation and its shield/jacket shall be re-applied to that repaired area. Any insulation reparation shall be also reported using the PAINTING SUMMARY REPORT from BMPS-B-50064 TYPICAL PAINTING & INSULATION QC FORMS FOR INSTALLATION.