## 000-C-TBE-60004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 9 | Jawad Alawi | Vendor to carry out the pickling and passivation per ASTM A380 requirement
2 | Call-out | 9 | Jawad Alawi | Per BMPS-C6 the preference is to carry out RT. However, if vendor want to proceed with TOFD, the requirements of BMPS-C6 in addition to API 934a Annex A shall be followed.
3 | Text Box | 21 | ddeluca | SEPARATORS
4 | Text Box | 21 | ddeluca | REACTORS
5 | Text Box | 25 | ddeluca | REACTORS NOT REFERENCED
6 | Text Box | 25 | ddeluca | SEPARATORS
7 | Casella di testo | 303 | Canal | Attach.#1: Scan Plan for UT ToFD exam. for Crowns - Circumferential welds (W11 to W17)
8 | Casella di testo | 306 | Canal | Attach.#2: Scan Plan for UT ToFD exam. for Heads - Meridian welds (from W12 to W16 & from W18to W22)
9 | Casella di testo | 309 | Canal | Attach.#3: Scan Plan for UT ToFD exam. for Circumferential weld Top Head to Shell (W10)
10 | Casella di testo | 312 | Canal | Attach.#4: Scan Plan for UT ToFD exam. for Shell Circumferential welds (W2 to W9)
11 | Casella di testo | 315 | Canal | Attach.#5: Scan Plans for UT ToFD exam. for Circumferential weld Bottom Head to Shell (W1)
12 | Casella di testo | 318 | Canal | Attach.#6: Scan Plans for UT ToFD exam. for Circumferential weld Skirt barrel III to Shell Barrel I(W25)
13 | Casella di testo | 320 | Canal | Attach.#7: Scan Plan for UT PA exam. for Nozzle M1 to Top Head (W32)
14 | Casella di testo | 323 | Canal | Attach.#8: Scan Plans for UT PA exam. for Nozzle N5 to Shell (W41)
15 | Casella di testo | 326 | Canal | Attach.#9: Scan Plans for UT PA exam. for Nozzle N11 to Bottom Head (W48)
16 | Casella di testo | 329 | Canal | Attach.#10: Scan Plans for UT PA exam. for Nozzle N9-N10 to Bottom Head (W42-W45)
17 | Call-out | 609 | Jawad Alawi | If all variables of the existing procedures are similar to BMP reactors variables it is accepted to use the existing procedures.
18 | Text Box | 618 | Adnan Alothman | Vendors for internals to be from the AVL, or to be approved by licensor/owner.