## 000-D-RPT-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Edgardo | General comment: In order to finalize the queries raised by Contractor in this document, Bapco recommends that a meeting among Bapco and Contractor be held to discuss them.
2 | Call-out | 1 | Mahdi Ali | UNITS
3 | Text Box | 1 | MAK | Use the latest cover page.
4 | Typewritten Text | 2 | Nabeel | delete
5 | Call-out | 2 | Abdul Rahim | Technip to ensure for so many works on tanks project schedule is achievable
6 | Call-out | 3 | Edgardo | prove
7 | Call-out | 3 | Edgardo | Provision of temporary connection to existing manway to be considered only in case the said tank could not be taken out of service (OOS) during the BMP construction phase
8 | Call-out | 3 | Edgardo | The suitability checks shall cover all items such as those related to constructability, operability, safety, maintainability, etc, of thenew nozzle connections
9 | Call-out | 4 | Edgardo | It should be noted that installation of the new heating coils will also require installation of pipe supports that may need to be welded on the tank bottom
10 | Call-out | 4 | Edgardo | Owner prefers that all permanent nozzles shall be installed on the tanks. However,such installation of permanent nozzles are dependent on the tank availability and the operational requirements of the company. Hence, the option for temporary connection on the manway can be considered if the tank cannot be under OOS during the BMP phase.
11 | Call-out | 5 | Abdul Rahim | regardless the size of nozzle tank needs to be hydrotested.
12 | Text Box | 5 | Edgardo | The above works involve also the installation of the required pipe supports and access platforms for the valves to be installed at roof. Contractor to assess whether such works can be done while the tank is in operation
13 | Call-out | 6 | MAK | Add 0 before 56
14 | Call-out | 6 | Abdul Rahim | please discuss this method
15 | Call-out | 6 | Edgardo | Refer to BMP-CON-LET-00037 for suction nozzle installed at 56D946
16 | Text Box | 6 | Edgardo | The suction nozzle on the shell is also acceptable
17 | Call-out | 6 | Abdul Rahim | This kind of work is being executed at Bapco with no complication
18 | Callout | 7 | Abdulla Al Ansari | Rim-seal system and installation of double (primary/secondary) seals applicability need to be confirmed by EPC Contractor for this tank basis its construction design and storage service according to the Owner's relevant specifications to install/retrofit double seals to minimize VOC emissions from floating roof tanks.
19 | Call-out | 7 | Edgardo | The subcontractors shall be prequalified in accordance with the agreed project procedures.
20 | Typewritten Text | 8 | Nabeel | Add note: EPC to study and advise on any special requirements for fire fighting system on the MTBE tanks
21 | Typewritten Text | 8 | Nabeel | EPC contractor to confirm the suitability of rivited tank for the MTBE service
22 | Call-out | 8 | Abdul Rahim | for new crude tanks at Refinery Tank Farm contractor is responsible for foam system
23 | Text Box | 9 | Edgardo | Owner has provided in the BMPS project specs the applicable specification for the tank
24 | Text Box | 10 | Edgardo | Please refer to Section 6 of BMPS-D5 for requirements regarding spill control.
25 | Text Box | 11 | Edgardo | As stipulated in BMP-CON-LET-00035, Contractor is requested to review his planning / sequencing and advise if any of the proposed OOS dates need to be adjusted to align with the schedule requirements and scope of work
26 | Call-out | 11 | Abdul Rahim | number of tie ins are required for each tank, in order to determine duration of tank outage. This is missing
27 | Call-out | 11 | Abdul Rahim | this is not correct, when some units will be planned for T&I products needs to be stored. we will explain
28 | Text Box | 12 | MAK | Add page header and number for this attachment.
29 | Call-out | 12 | MAK | General Comment: Add 0 before 50DXXX and 56DXXX in the entire document and table. Apply this change in other documents and drawings as well.
30 | Typewritten Text | 17 | Nabeel | Gasoline Service
31 | Call-out | 18 | Abdul Rahim | wrong service