## 000-E-MRQ-60001-001-RAP-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 5 | Fatema Hashem | INCLUDE ALL RELEVANT CLG STANDARD SPECIFICATIONS FOR HIGH PRESSURE EXCHANGERS
2 | Call-out | 5 | Ali Kadhem | Include UOP Standard 3-17 and 4-12. Those standards are mentioned in the exchangers datasheet notes.
3 | Text Box | 8 | Mahdi Ali | Remove the space
4 | Text Box | 9 | Mahdi Ali | Align the text properly
5 | Text Box | 24 | Ahmed Habib | Maintenance
6 | Text Box | 24 | Omran A | Laptop shall be purchased basis area classification which laptop will be used.
7 | Call-out | 25 | Ali Kadhem | Please review the shell and tubes design pressure. It appears to be formatting issue.
8 | Callout | 25 | rob.urban | REVIEW AND CORRECT THESE NUMBERS
9 | Call-out | 25 | Rashed Almudahka | confirm shell & tube design pressure for the equipment, especially the ones with empty spaces.
10 | Text Box | 25 | Mahdi Ali | Remove spaces between the sequence number and suffix
11 | Text Box | 30 | Mahdi Ali | Indicate the document number
12 | Callout | 30 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1006 ALSO APPLY TO 018E2006
13 | Call-out | 41 | Rashed Almudahka | Tube sheet Temp. shall be as per higher side temp. i.e. tube side. Please modify
14 | Call-out | 41 | Ahmed Bucheeri | SB 564 UNS N08825
15 | Call-out | 42 | Rashed Almudahka | Several specifications e.g. BMPS-M1, BMPS-E1, BMPS-C3, etc. are not included in the GAD of some equipment, e.g. 018E2006, 018E2007, etc. please clarify.
16 | Call-out | 42 | Rashed Almudahka | Note 18 ((NOT FOR PROCUREMENT, EPC CONTRACTOR TO VERIFY)) to be removed from this data sheet and wherever applicable.
17 | Text Box | 43 | Mahdi Ali | Add the equipment number
18 | Text Box | 44 | Mahdi Ali | Add equipment number
19 | Text Box | 45 | Mahdi Ali | Add equipment number
20 | Callout | 46 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1007 ALSO APPLY TO 018E2007
21 | Text Box | 46 | Mahdi Ali | Indicate the document number
22 | Call-out | 47 | Rashed Almudahka | Provide the basis of modifying shell side temperature to 400F from 450F as per FEED
23 | Callout | 51 | rob.urban | THIS EXCHANGER WILL NOT BE STEAMED OUT
24 | Text Box | 54 | Ahmed Bucheeri | SMLS
25 | Text Box | 56 | Ahmed Bucheeri | SA 350 GR LF2
26 | Call-out | 56 | Rashed Almudahka | Tube sheet Temp. shall be as per higher side temp. i.e. shell side. Please modify
27 | Text Box | 58 | Mahdi Ali | Add equipment number
28 | Text Box | 59 | Mahdi Ali | Add equipment number
29 | Text Box | 60 | Mahdi Ali | Add equipment number
30 | Text Box | 61 | Mahdi Ali | Add document numebr
31 | Callout | 62 | Fatema Hashem | GENERAL COMMENT: ADVISE WHY THIS DATA HAS NOT BEEN COMPLETED. IT IS INCLUDED IN LICENSOR DATASHEET
32 | Text Box | 66 | rob.urban | STEAM OUT SHALL NOT BE APPLIED FOR SS EQUIPMENT AND LINES IN THE HP LOOP. THIS IS APPLICABLE FOR ALL EXCHANGERS. DIFFERENT CLEANING PROCEDURES TO BE FOLLOWED
33 | Callout | 67 | Fatema Hashem | THE HEATING CURVE DATA DOES NOT MATCH THE UPDATED EXCHANGER DATASHEET FROM CLG. REVIEW AND UPDATE
34 | Callout | 71 | Fatema Hashem | ENSURE THAT ALL RELEVANT CLG SPECS ARE INCLUDED IN THE MATERIAL REQUISITION
35 | Text Box | 73 | Mahdi Ali | Use latest border that is part of the homogenization procedure
36 | Call-out | 73 | Ahmed Bucheeri | Either to mention the W.O.L material "SS347" in the same row OR to add another row for W.O.L details
37 | Text Box | 74 | Mahdi Ali | Use latest border that is part of the homogenization procedure
38 | Text Box | 75 | Mahdi Ali | Use latest border that is part of the homogenization procedure
39 | Text Box | 75 | Mahdi Ali | Add equipment tag
40 | Text Box | 76 | Mahdi Ali | Use latest border that is part of the homogenization procedure
41 | Text Box | 76 | Mahdi Ali | Add equipment number
42 | Text Box | 77 | Mahdi Ali | Use latest border that is part of the homogenization procedure
43 | Text Box | 81 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials from 2.25 Cr 1Mo and SS347 â€œFEED data sheetâ€ to the current material CS base metal with SS410 cladding material, though both design temperature and pressure of the shell been increased.
44 | Call-out | 81 | Jawad Alawi | Seamless
45 | Text Box | 83 | rob.urban | NO STEAM OUT. SEE PREVIOUS NOTE
46 | Callout | 84 | Fatema Hashem | THE HEATING CURVE DATA DOES NOT MATCH THE UPDATED EXCHANGER DATASHEET FROM CLG. REVIEW AND UPDATE
47 | Call-out | 87 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials
48 | Call-out | 87 | Ahmed Bucheeri | To clarify the basis of changing the metallurgy from SS321 to SS410 & SS405
49 | Callout | 88 | Fatema Hashem | ENSURE THAT ALL RELEVANT CLG SPECS ARE INCLUDED IN THE MATERIAL REQUISITION
50 | Callout | 88 | Fatema Hashem | CORRECT REFERENCES TO OLD EQUIPMENT NUMBERS IN ALL LOCATIONS
51 | Call-out | 90 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials from 2.25 Cr 1Mo and SS347 â€œFEED data sheetâ€ to the current material CS base metal with SS410 cladding material, though both design temperature and pressure of the shell been increased.
52 | Call-out | 90 | Ahmed Bucheeri | Mention the W.O.L metallurgy OR add row for W.O.L details.
53 | Call-out | 90 | Ahmed Bucheeri | TP321
54 | Text Box | 91 | Mahdi Ali | Use latest border that is part of the homogenization procedure
55 | Text Box | 92 | Mahdi Ali | Use latest border that is part of the homogenization procedure
56 | Text Box | 92 | Mahdi Ali | Add Equipment number
57 | Text Box | 93 | Mahdi Ali | Add Equipment number
58 | Text Box | 93 | Mahdi Ali | Use latest border that is part of the homogenization procedure
59 | Text Box | 94 | Mahdi Ali | Use latest border that is part of the homogenization procedure
60 | Callout | 96 | Fatema Hashem | CHECK THE HP/HT VAP INLET FLOW WITH CLG DATASHEET
61 | Call-out | 98 | Jawad Alawi | Tubes shall be seamless for all heat exchangers
62 | Text Box | 100 | rob.urban | NO STEAM OUT. SEE PREVIOUS NOTE
63 | Callout | 101 | Fatema Hashem | THE HEATING CURVE DATA DOES NOT MATCH THE UPDATED EXCHANGER DATASHEET FROM CLG. REVIEW AND UPDATE
64 | Callout | 105 | Fatema Hashem | ENSURE THAT ALL RELEVANT CLG SPECS ARE INCLUDED IN THE MATERIAL REQUISITION
65 | Call-out | 107 | Rashed Almudahka | Tube sheet material is not complying to the updated EDP i.e. SA240 TP321, please clarify.
66 | Text Box | 107 | Mahdi Ali | Use latest border that is part of the homogenization procedure
67 | Text Box | 108 | Mahdi Ali | Use latest border that is part of the homogenization procedure
68 | Text Box | 109 | Mahdi Ali | Add equipment number
69 | Text Box | 109 | Mahdi Ali | Use latest border that is part of the homogenization procedure
70 | Text Box | 110 | Mahdi Ali | Use latest border that is part of the homogenization procedure
71 | Text Box | 110 | Mahdi Ali | Add Equipment number
72 | Text Box | 111 | Mahdi Ali | Use latest border that is part of the homogenization procedure
73 | Callout | 113 | Fatema Hashem | CHECK THE HP/HT VAP OUTLET FLOW WITH CLG DATASHEET
74 | Text Box | 118 | rob.urban | NO STEAM OUT. SEE PREVIOUS NOTE
75 | Callout | 119 | Fatema Hashem | REVIEW AND CORRECT MISTAKES IN SHEET NUMBERS
76 | Callout | 122 | Fatema Hashem | ENSURE THAT ALL RELEVANT CLG SPECS ARE INCLUDED IN THE MATERIAL REQUISITION
77 | Callout | 123 | Fatema Hashem | THE HEATING CURVE DATA FOR 18E1004 HAVE BEEN DELETED FROM TECHNIP DATASHEET. CHECK AND ADD
78 | Text Box | 124 | Mahdi Ali | Use latest border that is part of the homogenization procedure
79 | Text Box | 125 | Mahdi Ali | Use latest border that is part of the homogenization procedure
80 | Text Box | 126 | Mahdi Ali | Add equipment number
81 | Text Box | 126 | Mahdi Ali | Use latest border that is part of the homogenization procedure
82 | Text Box | 129 | Rashed Almudahka | comments on train-1 equipment are applicable for train-2 equipment and vice versa.
83 | Call-out | 140 | Ahmed Bucheeri | SB 564
84 | Callout | 150 | rob.urban | NO STEAM OUT FOR THIS EXCHANGER
85 | Text Box | 155 | Ahmed Bucheeri | SA 350 GR LF2
86 | Callout | 160 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1001 ALSO APPLY TO 018E2001
87 | Callout | 177 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1002 ALSO APPLY TO 018E2002
88 | Text Box | 180 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials from 2.25 Cr 1Mo and SS347 â€œFEED data sheetâ€ to the current material CS base metal with SS410 cladding material, though both design temperature and pressure of the shell been increased.
89 | Call-out | 186 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials
90 | Call-out | 186 | Ahmed Bucheeri | To clarify the basis of changing the metallurgy from SS321 to SS410 & SS405
91 | Call-out | 189 | Ahmed Bucheeri | TP321
92 | Call-out | 189 | Ahmed Bucheeri | To clarify the reasons behind downgrading the metallurgy of shell base metal and W.O.L materials from 2.25 Cr 1Mo and SS347 â€œFEED data sheetâ€ to the current material CS base metal with SS410 cladding material, though both design temperature and pressure of the shell been increased.
93 | Call-out | 189 | Ahmed Bucheeri | Mention the W.O.L metallurgy OR add row for W.O.L details.
94 | Callout | 194 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1003 ALSO APPLY TO 018E2003
95 | Callout | 211 | Fatema Hashem | ALL COMMENTS ON TRAIN 1 EXCHANGER 018E1004 ALSO APPLY TO 018E2004
96 | Callout | 220 | Fatema Hashem | REVIEW AND CORRECT MISTAKES IN PAGE NUMBERS
97 | Call-out | 230 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
98 | Call-out | 231 | Rashed Almudahka | Provide the specification and grade of carbon steel for tie rods and spacers
99 | Call-out | 231 | Rashed Almudahka | TYPICAL COMMENT FOR ALL #3HDU EXCHANGERS: Provide the basis of 135ft/sec for wind speed
100 | Text Box | 232 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 2 and 6) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on both sides. 2. Design for wet H2S service per UOP Standard Specification 4-11, Section 4.7 or 4-12, Section 3.5 on both sides. 6. Provide separated head closure design for hairpin type exchangers.
101 | Call-out | 235 | Rashed Almudahka | TYPICAL COMMENT FOR ALL #3HDU EXCAHNGERS: Weights & loading data table are not matching with the one in the GAD. please clarify.
102 | Call-out | 236 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid inlet density, but for the tube side is for liquid outlet density. Please confirm.
103 | Call-out | 243 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
104 | Call-out | 244 | Rashed Almudahka | Provide the specification and grade of SS304 for channel cover gasket.
105 | Text Box | 245 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 2, 4, 6 and 7) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on both sides. 2. Design for wet H2S service per UOP Standard Specification 4-11, Section 4.7 or 4-12, Section 3.5 on tube side. 4. Do not use horizontal baffle cut for this item. 6. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 7. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle cut is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.4 as mentioned above.
106 | Call-out | 250 | Ahmed Bucheeri | Channel Cover material to be consistent in drawing and data sheet
107 | Call-out | 250 | Rashed Almudahka | TYPICAL COMMENT FOR ALL #3HDU EXCHANGERS (except 021E0009): TEMA type to be modified as D(MOD)EU per EDP & submitted data sheets.
108 | Call-out | 250 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density. For the tube side, the density mentioned in the EDP datasheet is for vapor inlet/outlet i.e. 0.4416 lb/ft3 and 0.3555 lb/ft3. Please confirm.
109 | Call-out | 256 | Ali Kadhem | It is noted that the shell side inlet operating pressure in the EDP Datasheet is 995psig. Please confirm
110 | Call-out | 256 | Ali Kadhem | It is noted that the shell side max allowable pressure drop in the EDP Datasheet is 9.7psi. Please confirm
111 | Call-out | 257 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
112 | Call-out | 258 | Rashed Almudahka | Provide the specification and grade for tie rods, spacers and channel cover gasket
113 | Call-out | 259 | Rashed Almudahka | note no.24 is clearly indicating the lining requirement. please clarify the purpose of note no.9
114 | Text Box | 259 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 2, 3 and 8) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on shell side, 2. Do not use horizontal baffle cut for this item. 3. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 8. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle type is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.2 as mentioned above.
115 | Call-out | 265 | Rashed Almudahka | Provide the specification and grade for baffles, tie rods and spacers MOC
116 | Call-out | 265 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density, but for the tube side is for liquid inlet density. Please confirm.
117 | Call-out | 271 | Ali Kadhem | It is noted the shell side inlet operating pressure in the EDP datasheet is 1012psig. please confirm
118 | Call-out | 271 | Ali Kadhem | It is noted the shell side max allowable pressure drop in the EDP datasheet is 9.6 psi. please confirm
119 | Call-out | 272 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
120 | Text Box | 274 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 4, 6 and 7) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on shell side. 4. Do not use horizontal baffle cut for this item. 6. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 7. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle type is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.4 as mentioned above.
121 | Call-out | 280 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density, but for the tube side is for liquid inlet density. Please confirm.
122 | Call-out | 282 | Rashed Almudahka | asset number to be corrected
123 | Call-out | 283 | Rashed Almudahka | as per note no.16 of the data sheet, number of baffles should be 13 nos. please clarify
124 | Call-out | 286 | Ali Kadhem | It is noted that the shell side max allowable pressure drop mentioned in the EDP datasheet is 4.7psi. please confirm.
125 | Call-out | 286 | Ali Kadhem | It is noted that the shell side inlet operating pressure mentioned in the EDP datasheet is 1019psig. please confirm.
126 | Call-out | 287 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
127 | Text Box | 289 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 3, 5 and 6) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on both sides. 3. Do not use horizontal baffle cut for this item. 5. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 6. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle type is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.3 as mentioned above.
128 | Call-out | 294 | Rashed Almudahka | Provide the specification and grade for Baffles, tie rods and spacers MOC
129 | Call-out | 294 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density (EDP Datasheet), but for the tube side is for vapor inlet density (H&MB). Please confirm.
130 | Call-out | 300 | Ali Kadhem | It is noted that the shell side maximum allowable pressure drop mentioned in the EDP Datasheet is 4.9psi. Please confirm.
131 | Call-out | 301 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
132 | Call-out | 302 | Rashed Almudahka | Provide the specification and grade for tie rods, spacers and channel cover gasket MOC
133 | Text Box | 303 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 3, 5, 6 and 7) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on both sides. 3. Do not use horizontal baffle cut for this item. 5. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 6. Use TEMA 'C' head with pass-partition similar to TEMA 'D' head. 7. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle type is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.3 as mentioned above.
134 | Call-out | 308 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density (EDP Datasheet), but for the tube side is for vapor inlet density (H&MB). Please confirm.
135 | Call-out | 308 | Rashed Almudahka | Provide the specification and grade for tie rods and spacers MOC
136 | Call-out | 315 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, Thickness, Pitch and Length) mentioned in this datasheet and the Licensor datasheet (EDP). Therefore, please obtain approval from the Licensor (UOP) for these changes.
137 | Text Box | 317 | Ali Kadhem | It is noted that some of the Licensor (EDP) datasheet notes (i.e. no.1, 2, 3 and 8) are not included in this datasheet. Please include those notes: 1. Design for hydrogen service per UOP Standard Specification 4-11, Section 4.6 or 4-12, Section 3.4 on shell side, 2. Do not use horizontal baffle cut for this item. 3. If a TEMA type C front head (channel integral with the tubesheet) is used, the material of the channel shall be the same as the tubesheet. 8. This item shall have a removable tube bundle or use a TEMA type CEU with a removable shell. It is noted that a vertical baffle type is specified in this datasheet, however, please include the licensor (EDP) datasheet note no.2 as mentioned above.
138 | Text Box | 323 | Ahmed Bucheeri | Channel Cover material in drawing and data sheet to be consistent
139 | Call-out | 323 | Ali Kadhem | It is noted that the fluid density for the shell side is for liquid outlet density, but for the tube side is for liquid inlet density. Please confirm.
140 | Call-out | 327 | Rashed Almudahka | As per note.24 of data sheet. it has to have 2 seal rods. please clarify