## 000-E-MRQ-60002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 3 | Mahdi Ali | CHANGE TO 001 TO 005
2 | Call-out | 3 | Mahdi Ali | ALIGN TEXT TO TABLE
3 | Call-out | 3 | Mahdi Ali | REMOVE SPACE BETWEEN TAG NUMBER AND SUFFIX
4 | Callout | 5 | Fatema Hashem | INCLUDE CHEVRON SPECIFICATION EXU-SU-2583 "SHELL AND TUBE HEAT EXCHANGERS FOR GENERAL REFINERY SERVICE"
5 | Callout | 5 | Fatema Hashem | MOVE REFERENCE NUMBER TO MIDDLE
6 | Call-out | 12 | Rashed Almudahka | There is no order of precedence within the technical documents per Annex 1 of the contract.
7 | Call-out | 16 | Rashed Almudahka | provide the basis of selecting 120mph as basic wind speed.
8 | Text Box | 22 | Ahmed Habib | Loaded with perpetual license and all necessary software.
9 | Text Box | 22 | AliRedha Malalla | does it mean "confirm"?
10 | Text Box | 22 | AliRedha Malalla | including any required testing devices.