## 000-E-MRQ-60003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 3 | Fatema Hashem | FOR 018 1RHCU EXCHANGERS, REFER TO OWNER COMMENTS MADE ON REV A DATASHEETS: BMP-ROC-TRI-00214
2 | Callout | 3 | Fatema Hashem | FOR 018 1RHCU EXCHANGERS, REFER TO OWNER COMMENTS MADE ON REV A DRAWINGS: BMP-ROC-TRI-00222
3 | Call-out | 3 | Ali Kadhem | For 1HRU (023) Exchangers, please refer to Owner’s comments provided in Rev.A of the Datasheets in transmittal BMP-ROC-TRI-00213. For 3HDU (021) Exchanger (021E0018A/B), please refer to Owner’s comments provided in Rev.A of the Datasheet in transmittal BMP-ROC-TRI-00220.
4 | Call-out | 4 | Ali Kadhem | For 1HRU (023) Exchangers, please refer to Owner’s comments provided in Rev.A of the Mechanical Drawings in transmittals BMP-ROC-TRI-00224 and BMP-ROC-TRI-00225. For 3HDU (021) Exchanger (021E0018A/B), please refer to Owner’s comments provided in Rev.A of the Mechanical Drawings in transmittal BMP-ROC-TRI-00223.
5 | Call-out | 8 | Rashed Almudahka | 2 year-trouble-free spare parts shall be included.
6 | Call-out | 15 | Rashed Almudahka | / rods
7 | Call-out | 18 | Rashed Almudahka | provide the basis of selecting raised face flanges, as it shall be in accordance with asset piping class.
8 | Call-out | 18 | Rashed Almudahka | provide basis of 120mph wind speed.
9 | Call-out | 19 | Ahmed Bucheeri | Advanced UT shall be used as the substitute of RT
10 | Call-out | 22 | Rashed Almudahka | thickness and dimension are minimum.
11 | Text Box | 23 | AliRedha Malalla | identifying filling provisions for
12 | Text Box | 24 | AliRedha Malalla | and testing (e.g. test rings)
13 | Call-out | 26 | Rashed Almudahka | there are several deviations from BMPS-E-50204. OWNER understands some tests become more stringent because of the special service, but there are other tests which either neglected or downgraded. please clarify.