## 000-E-MRQ-60004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | rob.urban | The Owner does not have the means to verify the calculations undertaken by the Contractor and can only verify certain data included within the report from available documentation. It is the Contractor’s responsibility to ensure correctness and accuracy of the data in line with the terms of the Contract.
2 | Text Box | 7 | Hasan Asad | Add: BMPS-S12
3 | Call-out | 15 | Rashed Almudahka | There is no order of precedence within the technical documents per Annex 1 of the contract
4 | Call-out | 17 | Rashed Almudahka | Please include the approved suppliers as per OWNER AVL
5 | Text Box | 26 | Omran A | to be in line with BMPSJ40
6 | Call-out | 165 | Ali Kadhem | The inlet operating pressure as per the EDP datasheet is 216.6psig. Please check and confirm.
7 | Call-out | 166 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
8 | Call-out | 166 | Ali Kadhem | The tube sheet design temperature as per the FEED datasheet is 500F. Please provide rational for this change
9 | Call-out | 171 | Ali Kadhem | The tube sheet design temperature as per the FEED datasheet is 500F. Please provide rational for this change
10 | Call-out | 178 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
11 | Call-out | 190 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
12 | Call-out | 205 | Ali Kadhem | It is noted that the tubes length mentioned in this datasheet is different than the Licensor datasheet (EDP). Please provide the rational for this change.
13 | Call-out | 220 | Ali Kadhem | The inlet operating pressure as per the H&MB i.e. upstream of FV40 is 137psig. Please check and confirm.
14 | Text Box | 221 | Ali Kadhem | It is noted that there are differences in the tubes dimensions/configuration (e.g. OD, thickness, pitch and length) mentioned in this datasheet and the Licensor datasheet (EDP). Please provide the rational for those differences.
15 | Call-out | 229 | Ali Kadhem | The drawing no. mentioned is for the Vacuum Drier Bottoms / Feed Exchanger 021E0001. Please check and revise.