## 000-G-MRQ-60003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Refer to page 2/7 to 7/7
2 | Cloud+ | 1 | MAK | Delete
3 | Cloud+ | 1 | MAK | Change to 1/7
4 | Cloud+ | 2 | MAK | Change to 2/7
5 | Cloud+ | 3 | MAK | Change to 3/7
6 | Cloud+ | 4 | MAK | Change to 4/7
7 | Cloud+ | 5 | MAK | Change to 5/7
8 | Cloud+ | 6 | MAK | Change to 6/7
9 | Cloud+ | 7 | MAK | Change to 7/7
10 | Cloud+ | 8 | MAK | Change to Bapco Doc. No. on all pages.
11 | Callout | 8 | Fatema Hashem | FOR 018 1RHCU PUMPS, REFER TO OWNER COMMENTS MADE ON REV B DATASHEETS: BMP-ROC-TRI-00389
12 | Callout | 8 | Mahdi Ali | EQUIPMENT TAG SHALL NOT CONTAIN SPACES
13 | Callout | 9 | Mahdi Ali | REFINERY SOUTH FLARE
14 | Callout | 9 | Fatema Hashem | FOR 018 1RHCU PUMPS, REFER TO OWNER COMMENTS MADE ON REV B DATASHEETS: BMP-ROC-TRI-00389
15 | Callout | 10 | Mahdi Ali | REFINERY SOUTH FLARE
16 | Text Box | 13 | David.Jimenez | There are some BMPs related to Steam Turbines that have not been included in this list. This includes, but it is not limited to the following documents: BMPS-K-50412 BMPS-K-50413 BMPS-K-50403 (which is the steam turbine data sheet template to be filled) BMPS-SD-L-10165 BMPS-SD-L-10225 (Please consider this as a typical comment concerning all MR of pumps that use steam turbines as a driver)
17 | Call-out | 17 | Edgardo | Please replace 1Flare with Refinery South Flare;
18 | Call-out | 20 | Edgardo | Please replace 1Flare with Refinery South Flare
19 | Callout | 23 | David.Jimenez | And what about the document for steam turbine drawings? Is that to be included in A2001 or provided separately?
20 | Text Box | 27 | Rashed Almudahka | Add a list of abbreviations mentioned in this MR, e.g. TTSJV, PURCHASER, etc.
21 | Text Box | 27 | Isamu | There is no priority dcuments to prevail in case of conflisct. Please refer to BMPS-A and correct accordingly
22 | Text Box | 28 | AliRedha Malalla | shims SS, grounding lugs...
23 | Call-out | 29 | Rashed Almudahka | JV to confirm item no. k is part of pump supplier scope.
24 | Text Box | 31 | Omran A | Owner's rep and
25 | Call-out | 31 | Ahmed Habib | Owner Automation Engineer shall be added
26 | Callout | 36 | Mahdi Ali | AVOID THE USE OF THE WORD 'NEW' IN THE ENTIRE DOCUMENT.
27 | Call-out | 39 | Rashed Almudahka | weights
28 | Call-out | 40 | Rashed Almudahka | capital spares shall be added as per ITB volume 2, section 6.5, attachment-1.
29 | Call-out | 46 | Ebrahim | Add a note: Selection of this vendor is subjected to Pre-Qualification exercise. Refer to AVL
30 | Call-out | 47 | Ebrahim | Add a note: Selection of this vendor is subjected to Pre-Qualification exercise. Refer to AVL
31 | Call-out | 55 | Ahmed Bucheeri | To be "W"
32 | Call-out | 66 | Ahmed Bucheeri | To be filled as per Table 14 for inspection level 3 as mentioned in this data sheet
33 | Text Box | 70 | David.Jimenez | Note 2
34 | Callout | 70 | David.Jimenez | Put reference to Note 15
35 | Text Box | 72 | Isamu | For all data sheet, seal flush piping and your added words of barrier shall be SS piping, welding and flanges. Tubes not acceptable
36 | Call-out | 73 | Ahmed Bucheeri | To be filled as per Table 14 for inspection level 3 as mentioned in this data sheet
37 | Text Box | 80 | Ahmed Bucheeri | YES
38 | Text Box | 80 | Ahmed Bucheeri | YES 10%
39 | Call-out | 87 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
40 | Call-out | 94 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
41 | Call-out | 101 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
42 | Call-out | 108 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
43 | Call-out | 115 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 2
44 | Call-out | 122 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 2
45 | Call-out | 129 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
46 | Callout | 133 | Fatema Hashem | REFER TO OWNER COMMENTS ON B REVISION: PLEASE NOTE THAT DIESEL FLUSHING OIL RETURN MAY BE ROUTED TO THESE PUMPS AND HENCE INCLUDE DIESEL PROPERTIES TOO WITH APPROPRIATE NOTE
47 | Call-out | 136 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
48 | Callout | 138 | Fatema Hashem | REFER TO OWNER COMMENTS ON REV B. OF THE DATASHEET: REFER TO JV RESPONSE TO COMMENTS MADE ON REV A WITH REGARDS TO NOTE 11:"note is referring to the flushing operation of flushing the heat exchangers with cold MVGO. Value of viscosity needs to be updated to 17.81cP according to the air cooler E0026 outlet viscosity". 1. PLEASE NOTE THIS IS A PUMP AND NOT A HEAT EXCHANGER, PLEASE MODIFY THE NOTE. 2. PLEASE NOTE THAT E0026 IS NOT AN AIR COOLER AND THAT IT IS NOT CONNECTED WITH THIS PUMP. I BELIEVE TTSJV ARE REFERRING TO THE VISCOSITY ON THE OUTLET OF E0023. 3. PLEASE CLARIFY WHERE THE VISCOSITY HAS BEEN UPDATED TO 17.81cP.
49 | Call-out | 143 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
50 | Call-out | 150 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
51 | Call-out | 155 | Ahmed Bucheeri | For rich amine service material class to be S8 as per API610. Clarify the selection of class A8
52 | Call-out | 157 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
53 | Call-out | 164 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
54 | Text Box | 171 | Ahmed Bucheeri | YES
55 | Text Box | 178 | Ahmed Bucheeri | YES
56 | Text Box | 185 | Ahmed Bucheeri | YES
57 | Call-out | 192 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
58 | Call-out | 199 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
59 | Call-out | 206 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
60 | Text Box | 209 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
61 | Text Box | 213 | Ahmed Bucheeri | YES
62 | Text Box | 222 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
63 | Text Box | 226 | Ahmed Bucheeri | YES
64 | Text Box | 229 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
65 | Call-out | 231 | Ahmed Bucheeri | To clarify the selection of class S8
66 | Text Box | 233 | Ahmed Bucheeri | YES
67 | Text Box | 236 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
68 | Text Box | 240 | Ahmed Bucheeri | YES
69 | Text Box | 244 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
70 | Call-out | 248 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
71 | Text Box | 251 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
72 | Call-out | 255 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
73 | Text Box | 258 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are incorporated in this MR.
74 | Call-out | 262 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3