## 000-G-MRQ-60005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Isamu | All seal flush and auxiliary seal flush piping plans including plans 52, 53A and 53B shall be stainless steel pipings, socket welded and connections shall be terminated with welded flanges. This is as clearly stated on each data sheet and deviation by EPC contractor is not acceptable as repeatedly discussed and indicated. Tubing is totally rejected and alternative material of construction is not acceptable The above statement shall be applicable to all API pumps is this MR and other MR for other pump types and all Vendors on earth can and will comply.
2 | Cloud+ | 1 | MAK | Refer to page 2/3/4
3 | Callout | 5 | Fatema Hashem | FOR 018 1RHCU PUMPS, REFER TO OWNER COMMENTS MADE ON REV B DATASHEETS: BMP-ROC-TRI-00411
4 | Cloud+ | 5 | MAK | Change to Bapco Doc. No. on all pages
5 | Callout | 6 | Fatema Hashem | FOR 018 1RHCU PUMPS, REFER TO OWNER COMMENTS MADE ON REV B DATASHEETS: BMP-ROC-TRI-00411
6 | Text Box | 20 | Isamu | Owner repeatedly commented that your order of priority is not correct and shall be removed. We made such comment on each MR but EPC contractor is ignoring such important comment. Please refer to BMPS-A1 and BMPS-A2 to have clear understanding to the order of priority and correct your MR accordingly.
7 | Text Box | 21 | Isamu | What is this ? Delete such vague confusing words and comply with the requirement mentioned on page 1 of this MR.l
8 | Text Box | 24 | Omran A | Owner &
9 | Text Box | 24 | Ahmed Habib | Owner Automation Engineer representitave shall be added
10 | Call-out | 47 | Ahmed Bucheeri | W
11 | Text Box | 48 | Ahmed Bucheeri | H R W R R
12 | Text Box | 48 | Ahmed Bucheeri | Pre-Inspection Meeting Suborders check Inspection of sub-ordered components N.D.E. on raw materials Explosion proof/Intrinsically safe certificates
13 | Text Box | 48 | Ahmed Bucheeri | Fill the missing items as per BMPS-G-50307_0
14 | Call-out | 57 | Ahmed Bucheeri | To specify the inspection class
15 | Text Box | 59 | Ahmed Bucheeri | Basis the specified inspection class and table No.14 NDE requirement to be filled
16 | Text Box | 63 | David.Jimenez | (Note 2) - Typ comment
17 | Text Box | 63 | David.Jimenez | Please include a reference to Note 17 - Typ comment
18 | Text Box | 66 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 2
19 | Text Box | 73 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
20 | Call-out | 78 | Ahmed Bucheeri | As per feed and EDP sheets the class is S1. To confirm the selection of class S5
21 | Text Box | 80 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 2
22 | Text Box | 87 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 2
23 | Text Box | 94 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
24 | Call-out | 99 | Ahmed Bucheeri | As per feed and EDP sheets the class is S1. To confirm the selection of class S5
25 | Text Box | 101 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
26 | Text Box | 108 | Ahmed Bucheeri | YES
27 | Callout | 111 | Fatema Hashem | REFER TO OWNER COMMENTS MADE ON REVISION A AND B, DIESEL TO BE ADDED AS A FLUID
28 | Text Box | 115 | Ahmed Bucheeri | YES
29 | Text Box | 122 | Ahmed Bucheeri | YES
30 | Text Box | 129 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
31 | Text Box | 136 | Ahmed Bucheeri | To be filled as per table No.14 and inspection class 3
32 | Text Box | 139 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are added along with this MR
33 | Text Box | 143 | David.Jimenez | Please remove this blank sheet
34 | Text Box | 144 | Ahmed Bucheeri | YES
35 | Text Box | 154 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are added along with this MR
36 | Text Box | 158 | Ahmed Bucheeri | YES
37 | Text Box | 161 | A Albalooshi | General Comment: Please ensure latest revision of data sheets are added along with this MR
38 | Text Box | 165 | Ahmed Bucheeri | YES