## 000-G-TBE-60002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Ravi Kumar | REFER TBE JOINT REVIEW MEETING WITH TPFMC ON 6AUG'18. OBTAIN CLARIFICATIONS / CONFIRMATIONS FROM THE VENDOR ON ISSUES LISTED IN THE MINUTES. COMPLY WITH OTHER ADDITIONAL COMMENTS PRINTED IN THIS DOCUMENT
2 | Cloud+ | 3 | MAK | Add Bapco Doc. No. as well
3 | Cloud+ | 3 | MAK | Add Bapco Doc. No. as well
4 | Text Box | 3 | MAK | General Comment: All references shall refer to Bapco Doc/Dwg numbers.
5 | Cloud+ | 3 | MAK | Add Bapco Doc. No. as well
6 | Text Box | 5 | MAK | Indicate the Attachment No.
7 | Callout | 5 | Mahdi Ali | JV IS OBLIGED TO PROVIDE THE 3D MODEL THAT CAN BE MODIFIED BY BAPCO WITHOUT THE REQUIREMENT FOR THE NATIVE SOURCE
8 | Text Box | 9 | MAK | Add Bapco Doc. No. on all pages
9 | Text Box | 9 | MAK | Indicate the Attachment No.
10 | Callout | 10 | Fatema Hashem | REVIEW VISCOSITY MAX AND MIN VALUES, NOT CONSISTENT WITH DATASHEET PROCESS REQUIREMENTS
11 | Callout | 10 | Fatema Hashem | MINIMUM FLOW SHOULD BE 3766 GPM PER DATASHEET PROCESS REQUIREMENTS
12 | Text Box | 10 | MAK | This is Attachment 1, reorder the attachments and move it to first.
13 | Callout | 10 | Fatema Hashem | ADD PUMPING TEMPERATURE
14 | Callout | 10 | Fatema Hashem | MAX DIFFERENTIAL PRESSURE SHOULD BE 20.2 PSI PER DATASHEET PROCESS REQUIREMENTS
15 | Callout | 10 | Fatema Hashem | THIS DATA IS NOT CONSISTENT WITH THE PROCESS REQUIREMENTS FROM LICENSOR. PLEASE REFER TO PUMP DATASHEET ATTACHMENT 1 AND 2
16 | Callout | 11 | Sankara | Does this arrow means compliance?
17 | Callout | 11 | Sankara | Should be LESS than 82dB.