## 000-J-BLD-60003-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | [1] Model | Omran A | P
2 | Cloud+ | [1] Model | MAK | 3H2 PLANT
3 | Text Box | [1] Model | Omran A | workstation
4 | Call-out | [1] Model | MAK | S
5 | Cloud+ | [1] Model | MAK | FEED BOOSTER PUMP HOUSE
6 | Cloud+ | [1] Model | MAK | Change the sign to ~
7 | Cloud+ | [1] Model | MAK | 1N2 PLANT
8 | Cloud+ | [1] Model | MAK | Why not replacing with the 160SRR01
9 | Cloud+ | [1] Model | MAK | Adjust the text inside border
10 | Callout | [1] Model | Francis L | Include Tank gauging requirements for new tanks in new AC plant booster pumps area which are to be connected directly to the TGS in Refy Tank Farm control building. Indicate the same on dwgs 000-J-BLD-60004-001 and 000-J-BLD-60004-002, too.
11 | Callout | [1] Model | Francis L | LOOP was indicate instead of RING in other similar dwg ie. 000-J-BLD-60004-001. Please use one relevant word for both dwgs.
12 | Callout | [1] Model | Francis L | Amend to 016. Applies to all other relevant nos.
13 | Cloud+ | [1] Model | MAK | Align text to left
14 | Callout | [1] Model | Francis L | Remove "-"
15 | Callout | [1] Model | Francis L | Indicate tags complete with plant no. and move this clarification to Notes section. Not needed to be shown here.
16 | Cloud+ | [1] Model | MAK | Why not replacing with the 156SRR01
17 | Cloud+ | [1] Model | MAK | Why not replacing with the 158SRR01
18 | Cloud+ | [1] Model | MAK | Why not replacing with the 159SRR01
19 | Text Box | [1] Model | Ahmed Habib | General Comment: All Connection between Control Buildings and Satellite Rack Rooms shall be via FO
20 | Cloud+ | [1] Model | MAK | Why not replacing with the 157SRR01
21 | Cloud+ | [1] Model | MAK | 372D0279
22 | Callout | [1] Model | Francis L | Clarify
23 | Cloud+ | [1] Model | MAK | WHARVES SUBMARINE
24 | Call-out | [1] Model | Bachir M | Title should be : BMP OVERALL PROCESS CONTROL SYSTEM BLOCK DIAGRAM
25 | Cloud+ | [1] Model | MAK | FEED BOOSTER PUMP HOUSE
26 | Callout | [1] Model | Francis L | Indicate the following for these drawings: - REFERENCE DRAWINGS - Drawing number - Title Applies to ALL other Block diagrams.
27 |  | [1] Model | AutoCAD SHX Text | The present document or drawing is property of TECHNIP ITALY S.p.A. and shall not, under any circumstances, be totally or partially, directly or indirectly, transferred, reproduced, copied, disclosed or used, without its prior written consent, for any purpose and in any way other than that for which it is specifically furnished or outside the extent of the agreed upon right of use.
28 | Callout | [1] Model | Francis L | Indicate unit number to ALL existing and new control buildings ie. 080 for this building.
29 | Cloud+ | [1] Model | MAK | 050D1001/1002/1003/1004
30 | Text Box | [1] Model | mohamed.waleed | Please mention "EXISTING" or "NEW" to the Satellite Rack Rooms, to have consistency and clear understanding.
31 | Cloud+ | [1] Model | MAK | Why not replacing with the 154SRR01
32 | Cloud+ | [1] Model | MAK | 050D1001/1002/1003/1004
33 | Cloud+ | [1] Model | MAK | 4H2 PLANT
34 | Cloud+ | [1] Model | MAK | 372D0279
35 | Text Box | [1] Model | Omran A | Why both are having the same symbol ?
36 | Callout | [1] Model | Mahdi Ali | RECONSIDER MODIFYING THE TITLE
37 | Cloud+ | [1] Model | MAK | Don't use ( _ ) sign
38 | Text Box | [1] Model | MAK | General Comments: - Use the latest drawing borders that are part of the Homogenisation Procedure (000-A-PRO-50006-001). - Drawing borders shall not be exploded. Follow BMPS-A8. - Refer to the Homogenization Procedure for the correct Unit names. - The word NEW shall not be used. All these new areas at this stage are defined. Use the correct description.
39 | Callout | [1] Model | Francis L | Apply consistent location of OC scope ie. inside box. Applies to ALL.
40 | Cloud+ | [1] Model | MAK | Why not replacing with the 155SRR01
41 | Text Box | [1] Model | Omran A | Is there a detailed diagram ?? if yes, please add drawing NO.
42 | Cloud+ | [1] Model | MAK | Word NEW shall not be used.
43 | Cloud+ | [1] Model | MAK | COOLING WATER TOWER
44 | Callout | [1] Model | Francis L | Include 372
45 | Cloud+ | [1] Model | MAK | Enter correct no.