## 000-L-MST-50001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Delete
2 | Cloud+ | 1 | MAK | This document is a specification and not a method statement. thus the document type shall be 'TSP' and not 'MST'. Change the document number and change all the references to this document accordingly. However, if this document is a method statement then the title should be changed accordingly.
3 | Text Box | 4 | Ravi Kumar | In Section 1.4 add reference to 'Supplemental High Pressure Piping Requirements' specification of CLG EDP for 1RHCU. Check the pre-fabrication, inspection requirements in the said specification and amend this document as required
4 | Text Box | 4 | 300060 | ASME B31.3 and 31.1are also reference documents please add here in this section also.
5 | Text Box | 4 | 300060 | ASME B1.20.1 seal welding is mentioned in BMPS B1 as a reference document also please add.
6 | Cloud+ | 4 | MAK | Use Bapco doc. no.
7 | Text Box | 5 | 300060 | Please spell out exact limitations for this welding process as stipulated in BMPS-B1 para 8.
8 | Text Box | 5 | 300060 | Please add: Note: BMP IPMT Inspector(s) reserves the right to call for supplementary inspection and NDE. The costs for such supplementary testing where required to clarify inconclusive or questionable examination results by RT.
9 | Callout | 8 | Nalini Mohan | B31A is not covered in this table. Verify the list with all piping specs and incorporate in this table
10 | Callout | 14 | 300060 | Will Contractor be performing MT or PT on 316L Cladding? This is a dissimilar metal process so PT?
11 | Callout | 22 | 300060 | please add approval is required by BMP when NDE is changed in lieu of RT
12 | Callout | 22 | 300060 | Another reference document that should be added to "reference" section
13 | Cloud+ | 22 | MAK | Use Bapco doc. no.
14 | Text Box | 24 | 300060 | Rotate page to landscape for recording purposes.
15 | Text Box | 25 | 300060 | Weld symbols need to indicate max/min root gap/ root face and fill weld throat thicknesses in accordance with approved WPS/PQR