## 000-L-MST-60001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Mahdi Ali | THIS DOCUMENT IS A SPECIFICATIN AND NOT A METHOD STATEMENT. THUS THE DOCUMENT TYPE SHALL BE 'TSP' AND NOT 'MST'. CHANGE THE DOCUMENT NUMBER AND CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A METHOD STATEMENT THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY
2 | Callout | 1 | Mahdi Ali | CHANGE MATERIAL CLASS TO 'A'
3 | Callout | 3 | Abdul Rahim | Is Refinery Tank Farm part of this
4 | Callout | 3 | Abdul Rahim | Is the assumption that Wharf will be under separate contract
5 | Callout | 3 | Abdul Rahim | how about Refinery / Sitra transfer lines
6 | Text Box | 3 | steven.coyne | Fig. 1 -
7 | Text Box | 4 | steven.coyne | Fig. 1 BAPCO REFINERY COMPLEX
8 | Text Box | 4 | steven.coyne | required
9 | Callout | 5 | Chandrahasan D | <Add> Trade Testing of laser survey personnel, Testing and tagging of survey equipments, prior to survey when working in Brown field areas.
10 | Typewritten Text | 5 | steven.coyne | ,
11 | Callout | 5 | Abdul Rahim | required
12 | Callout | 5 | Abdul Rahim | and risk assessment
13 | Pen | 5 | steven.coyne | N
14 | Callout | 5 | Abdul Rahim | the equipment shall be suitable for classified area
15 | Pen | 5 | steven.coyne | •
16 | Callout | 5 | Abdul Rahim | and without any risk
17 | Text Box | 5 | steven.coyne | prior to arrival at site.
18 | Text Box | 5 | steven.coyne | Delete duplicate statement from above.
19 | Callout | 5 | Abdul Rahim | without any
20 | Callout | 5 | Abdul Rahim | add (Brown Field)
21 | Pen | 5 | steven.coyne | •
22 | Text Box | 5 | steven.coyne | Some of this is duplicated in section 4, probably best to combine this first sentence into section 4
23 | Callout | 5 | Abdul Rahim | where gases and hydrocarbon are present
24 | Callout | 5 | Abdul Rahim | prior to
25 | Callout | 6 | Abdul Rahim | under permit to work
26 | Callout | 6 | Chandrahasan D | <add after Refinery>Sitra Tank farm benchmark as applicable.
27 | Callout | 7 | Mahdi Ali | ALL TAGGING FROM THE 3D LASER SCAN SHALL COMPLY TO BAPCO REQUIREMENTS AND AS PER BMPS-A8
28 | Callout | 7 | Mahdi Ali | LEICA
29 | Text Box | 8 | steven.coyne | Re-number Fig. 2 and .3 if you make the change in section 3
30 | Text Box | 9 | steven.coyne | Fig. 2
31 | Text Box | 10 | steven.coyne | Fig. 3
32 | Text Box | 11 | steven.coyne | 3
33 | Text Box | 11 | steven.coyne | 2