## 000-L-PQP-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 1 | Mahdi Ali | CHANGE THE MATERIAL CLASS FOR THIS DOCUMENT TO 'A' INSTEAD OF 'L'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDINGLY
2 | Text Box | 1 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
3 | Note | 1 | steven.coyne | PMI Inspection report as described in PQP 000-A-PRO-50039-001 not listed.
4 | Note | 2 | steven.coyne | Form PMI Report QC 23 not listed is this not used here?
5 | Cloud+ | 3 | Yousif Ahmadi | A
6 | Cloud+ | 3 | Yousif Ahmadi | A
7 | Cloud+ | 4 | Yousif Ahmadi | A
8 | Note | 4 | steven.coyne | Note (3) applies to F1 Thru to F6
9 | Note | 5 | steven.coyne | No reference to W09 in the document what is this?