## 000-L-PQP-50004-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | 2 | Jawad Alawi | FLANGES BOLT TENSIONING / TORQUING FORM
2 | Call-out | 2 | RASHED SHOWAITER | Recommendation: to include Quality Control Form for FLANGE/BOLT/GASKET
3 | Text Box | 2 | 300060 | What about Preservation provisions after reinstatement?
4 | Callout | 3 | 300060 | Piping Special Items e.g. exhausts, bird screens , vents etc. could require a check sheet
5 | Callout | 3 | 300060 | Piping Special Items e.g. exhausts, bird screens , vents etc. could require a check sheet
6 | Callout | 3 | 300060 | Piping Special Items e.g. exhausts, bird screens , vents etc. could require a check sheet
7 | Callout | 3 | 300060 | Rename column to REFERENCE DOCUMENTS, the column can be populated with applicable specs and codes , procedures, isometrics, P&ID,s etc
8 | Text Box | 3 | 300060 | Section for H/W/S for Preservation if Applicable.
9 | Typewritten Text | 4 | Newlito Diaz | (4) Acceptance criteria and/or each activity inspection form shall be indicated and referred as part of item 1 (Detailed Procedure).
10 | Callout | 4 | 300060 | These legends were not found to be used in this document
11 | Call-out | 4 | Newlito Diaz | to be added
12 | Call-out | 5 | Newlito Diaz | consider as commented to allow discreet or phased walkdown/early Precom/handover by sub-system (when necessary) to be updated to all forms.
13 | Text Box | 5 | steven.coyne | Other? is this box required
14 | Typewritten Text | 5 | Newlito Diaz | PC&C procedure/document ref. no.
15 | Typewritten Text | 5 | Newlito Diaz | SUB-SYSTEM:
16 | Typewritten Text | 5 | Newlito Diaz | SUP:
17 | Typewritten Text | 5 | Newlito Diaz | SYSTEM:
18 | Call-out | 5 | Newlito Diaz | To be added and updated to all forms.
19 | Typewritten Text | 5 | Newlito Diaz | UNIT:
20 | Call-out | 5 | Newlito Diaz | What about cleaning method for Pigging?
21 | Cloud+ | 5 | Mohamed Ayyash | What is SUP ?
22 | Text Box | 6 | steven.coyne | Same comment as page 5
23 | Callout | 6 | 300060 | Typical for all forms : what information is required here ?
24 | Callout | 6 | 300060 | Typical for all forms: add a box somewhere so that the cleaning pack reference number can be recorded.
25 | Callout | 6 | 300060 | Typical for all forms: add sub system
26 | Callout | 6 | 300060 | Typical for all forms: Change order to UNIT - SUP - SYSTEM -SUB SYSTEM on all forms
27 | Callout | 6 | 300060 | Typical to all forms: Revision number required
28 | Callout | 6 | 300060 | Typical to all forms: Change to show the Site Inspection Extent for each party. eg. HOLD ,WITNESS or REVIEW .Not all parties will be witnessing.
29 | Callout | 10 | 300060 | add a column for the cleanliness requirement
30 | Callout | 10 | 300060 | add the flow rate required to be achieved
31 | Text Box | 10 | Hasan Asad | For major machineries, vendor procedure and inspection and test cafeteria's to be followed and the final acceptance shall be granted by the vendor specialist.
32 | Call-out | 12 | Newlito Diaz | Complete the wording as; "REINSTATEMENT AFTER LINE CLEANING"
33 | Callout | 15 | 300060 | add a box to record the Gross Leak Test Pack reference number
34 | Call-out | 21 | Jawad Alawi | Add Set pressure value
35 | Typewritten Text | 22 | Newlito Diaz | PERMANENT
36 | Typewritten Text | 22 | Newlito Diaz | TEMPORARY
37 | Call-out | 22 | Newlito Diaz | to be added
38 | Typewritten Text | 24 | Newlito Diaz | 5. PC&C procedure/document ref. no.
39 | Call-out | 24 | Newlito Diaz | 6
40 | Callout | 24 | 300060 | add a box to record UNIT - SUP - SYSTEM - SUB SYSTEM
41 | Call-out | 24 | Newlito Diaz | PC&C procedure/document ref. no. (to be inserted as no. 5) and Remarks (as no. 6)
42 | Callout | 25 | 300060 | populate the column
43 | Callout | 26 | 300060 | These legends are not used in this document
44 | Callout | 34 | 300060 | add a box to record UNIT - SUP - SYSTEM - SUB SYSTEM
45 | Typewritten Text | 34 | Newlito Diaz | What about Commissioning forms for the following; 1. AGR hot water circulation 2. Hot Hydrogen Integrity Test 3. Condensate Flushing and Acceptance