## 000-L-TSP-50009-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 7 | David.Jimenez | and isometrics | Noted. BAPCO Comment has been included. | Y
2 | Call-out | 7 | Raj | Chemical compatibility of the desired service with FRP shall be confirmed prior to fabrication | Noted. BAPCO Comment has been included. | Y
3 | Call-out | 7 | Raj | Long radius smooth turn elbows shall be used in all cases Standard flanges with neck length adequate to accommodate a butt joint shall be joined to the plain ends of standard elbows | JV confirmed that long radius elbows will be used, according to the relevant CC description. JV clarified that all flanges having size 24" and greater have been defined as welding neck type suitable for the joining with butt & wrap type pipes and fittings (according to BMPS-L2). | N
4 | Callout | 7 | JaiMun.Oh | The SUPPLIER shall propose and supply the construction spare and the training pipes. | Noted. BAPCO Comment has been included. | Y
5 | Text Box | 8 | JaiMun.Oh | SUPPLIER shall provide export permit for Resin and Additives if required. MSDS and the estimated Q'ty for Resin and Additives shall be provided by SUPPLIER for application of import permit. | Noted. BAPCO Comment has been included. | Y
6 | Callout | 10 | Yousif Ahmadi | or any other tools | Noted. BAPCO Comment has been included. | Y
7 | Callout | 12 | Yousif Ahmadi | 3.2.1.3 | Noted. BAPCO Comment has been included. | Y
8 | Callout | 16 | David.Jimenez | Is there any criteria (such size, service, etc) to determine whether stress analysis should apply or not? No reference to project general stress specification? | Checking level of stress analysis for GRP piping lines shall be agreed with the SUPPLIER as required by BMPS-L10. No reference will be included: stress analysis will be performed according to SUPPLIER standard methodology. | N
9 | Text Box | 20 | Nalini Mohan | Training to OWNER inspection team shall be provided for field inspection and testing. | Noted. BAPCO Comment has been included. | Y
10 | Callout | 23 | Yousif Ahmadi | for each 100 length of pipe produced | The comment will not be implemented: a pipe lot shall consist of 100 pipe lengths or a fraction thereof as defined in para. 4.3. | N
11 | Callout | 23 | Yousif Ahmadi | for each 100 length of pipe produced | The comment will not be implemented: a pipe lot shall consist of 100 pipe lengths or a fraction thereof as defined in para. 4.3. | N
12 | Callout | 23 | Yousif Ahmadi | for each 100 length of pipe produced | The comment will not be implemented: a pipe lot shall consist of 100 pipe lengths or a fraction thereof as defined in para. 4.3. | N
13 | Callout | 25 | Yousif Ahmadi | one or Two? | JV confirmed that ONE spool for each size shall be prepared by the SUPPLIER | Y
14 | Call-out | 25 | Jawad Alawi | Specify the reference | Reference shall be made to para. 4.3.1 | Y
15 | Callout | 25 | Yousif Ahmadi | Which paragraph?? There is no 9.2.1 | Reference shall be made to para. 4.3.1 | Y
16 | Callout | 27 | Yousif Ahmadi | Per AWWA below to be included: (1) the phrase ANSI/AWWA C950; (2) nominal pipe size, cell classification, and diameter series; (3) AWWA pressure class; (4) stiffness class; and (5) manufacturer’s mark and identity code Check and confirm | Noted. BAPCO Comment has been included. | Y
17 | Callout | 27 | JaiMun.Oh | Spool Piece Number | Noted. BAPCO Comment has been included. | Y
18 | Text Box | 30 | Nalini Mohan | Since this class of piping is used for oily water sewer maximum temperature faced due to draining of hot liquids (during plant upset condition) shall be ascertained and informed to supplier. Currently RXB30 limits the design temperature to 165degF. During upset conditions liquids beyond 165degF will be drained to sewer system. | Design Temperature for PLC RXB30 (RTRP - Polyester) is 140degF (refer to BMPS-L2): to be clarified. Please note that the upset condition of 165degF could result as inappropriate for the polyester resin: the suitability of the material to be confirmed by the SUPPLIER | Y