## 000-M-STD-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Joon Cho | Denote Connection method (by field welding or bolting) with other structure or object
2 | Text Box | 1 | Erwin.Lugue | Section View?
3 | Text Box | 1 | Chandrahasan D | <Include> Standard drawing index sheet for all standard drawing related steelworks and a separate index sheet concrete works
4 | Callout | 1 | Mahdi Ali | SHOW DIMENSION BETWEEN HOLES
5 | Text Box | 1 | Erwin.Lugue | View?
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Callout | 1 | Chandrahasan D | Sl.NO or Type. If Type, include a heading under the Elevation detail (viz. Typical Elevation of Davit Type 1-11)
8 | Callout | 1 | Joon Cho | Complete
9 | Callout | 1 | Mahdi Ali | SHOW DIMENSTION BETWEEN BOLTS
10 | Callout | 1 | Salman Almajed | 10025
11 | Text Box | 1 | Erwin.Lugue | View?
12 | Callout | 1 | Mahdi Ali | SHOW DIMENSION WITH REFERENCE TO THE EDGE OF THE PLATE VERTICALLY.
13 | Callout | 1 | Chandrahasan D | Safe Lifting Load?? Include a column to show maximum test load considered in the design
14 | Callout | 1 | Erwin.Lugue | To include note in Arabic
15 | Text Box | 1 | Chandrahasan D | Typical Elevation of Davit Type 1-11??
16 | Cloud+ | 1 | MAK | Delete