## 000-M-STD-50005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | Salman Almajed | Change the beak line to reflect tube section (Typical).
2 | Text Box | 1 | Salman Almajed | General Comments: - Add reference drawing "General notes for steel structures". - Include all abbreviations (Ex. HB, SC, BC etc.). - The type of lines (dashed or continuous) used in the plan of HB-1 to HB-6 does not represent the actual connection details. It appears to be a bottom view of the connection. Please check all the plan details and verify.
3 | Callout | 1 | Salman Almajed | Exact dimensions are not required to be mentioned in standard drawings. These dimension are to be developed during fabrication drawing.
4 | Callout | 1 | Joon Cho | WP (Working Point) typical
5 | Callout | 1 | Chandrahasan D | Stiffeners missing??
6 | Callout | 1 | Chandrahasan D | Clarance typical
7 | Callout | 1 | Salman Almajed | Add the type of bracing (Angle, T-section, etc.) - Typical comment
8 | Callout | 1 | Erwin.Lugue | Why 2 plates? This gusset plate can be shop welded to the beam
9 | Callout | 1 | Chandrahasan D | Review and modify title block content to comply with BMPS -A8
10 | Cloud+ | 1 | Salman Almajed | If this is a double-angle bracing, then separate the angles to allow for packing plates.
11 | Callout | 1 | Chandrahasan D | Stiffeners ? Check
12 | Cloud+ | 1 | MAK | Delete
13 | Callout | 1 | Salman Almajed | Show dashed lines
14 | Callout | 1 | Chandrahasan D | Stiffeners missing?
15 | Callout | 1 | Salman Almajed | STIFFENER
16 | Cloud+ | 1 | Salman Almajed | This detail does not reflect the sectional cut line on the plan. Please check the detail or modify the sectional cut plane line of the plan to suit this detail. (Typical comment)
17 | Callout | 1 | Erwin.Lugue | Show the edge distances
18 | Cloud+ | 1 | Salman Almajed | Show dimension lines
19 | Text Box | 1 | Chandrahasan D | Many of the connection to the web may require stiffener plate on the far side. How this will be addressed?. Verify and revise the details. Also no details are available here to show column connected with beams on both sides. Will it be covered in separate drawing?
20 | Callout | 1 | Erwin.Lugue | Indicate welds
21 | Callout | 1 | Salman Almajed | Add weld symbol.
22 | Cloud+ | 1 | Salman Almajed | Change the beak line to reflect circular rod section (Typical).
23 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
24 | Cloud+ | 1 | Salman Almajed | Enlarge the text to match the other section headings
25 | Cloud+ | 1 | MAK | NTS
26 | Cloud+ | 1 | Salman Almajed | Use uppercase letter (Typical).
27 | Callout | 1 | Salman Almajed | Show dashed lines
28 | Callout | 1 | Chandrahasan D | Use abbreviations already defined in the std drawing or full text
29 | Cloud+ | 1 | Salman Almajed | Use different letters for different sections, to avoid confusion (Typical).
30 | Callout | 1 | Salman Almajed | Show dashed lines for the web
31 | Callout | 1 | Erwin.Lugue | Check for necessity of stiffeners
32 | Callout | 1 | Chandrahasan D | GAP (Typ)
33 | Callout | 1 | Erwin.Lugue | Show the edge distances, plate dimensions, gaps,etc.