## 000-Q-STD-50002-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | giovanny.rodriguez | ADD A NOTE TO NOTIFIED THAT THIS DOCUMENT MUST BE REVIEWED IN CONJUNCTION WITH BMPS-C-50116 & BMPS-C-50101 STD.
2 | Cloud+ | 1 | MAK | Delete
3 | Text Box | 1 | Erwin.Lugue | Details are applicable only to standard support saddles as per BPMS-C-50101, & BMPS-C-50116
4 | Callout | 1 | Erwin.Lugue | Details showing full embedded plate. Where are these going to be used?
5 | Callout | 1 | Erwin.Lugue | Embedded plates or PTFE Teflon?
6 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
7 | Cloud+ | 1 | Erwin.Lugue | Grout shall be refererred to BPMS-Q2
8 | Cloud+ | 1 | MAK | NTS
9 | Text Box | 1 | giovanny.rodriguez | PLEASE, CHECK THAT NAMED VARIABLES ARE CONSISTENT WITH THOSE WITHIN BMPS-C-50116 STD; ALSO CHECK THAT TYPE OF SADDLE DESCRIBED ON STD IS IDENTICAL TO TYPE DESCRIPTION IN THIS DWG. IN ANY CASE, DOCUMENT INFORMATION BETWEEN BMPS STD & JV STD MUST BE CLEAR AND CONSISTENT
10 | Text Box | 1 | Erwin.Lugue | Provide references
11 | Text Box | 1 | Erwin.Lugue | Provide title of this plan view
12 | Text Box | 1 | Erwin.Lugue | Sliding Plate without teflon
13 | Cloud+ | 1 | MAK | STANDARD DRAWING CONCRETE WORKS SLIDING PLATES TYPICAL DETAILS
14 | Callout | 1 | Erwin.Lugue | Supplied and to be installed by the Mechanical Subcontractor
15 | Callout | 1 | Erwin.Lugue | This will be mistaken for embedded plates. Change the Fill hatch.
16 | Text Box | 1 | Erwin.Lugue | View ?