## 000-R-GAD-60002-001-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page [1] Model | MAK | 000 - COMMON
2 | Call-out | Page [1] Model | MAK | Why the alignment of this title is different than the one in sheet 002? The Owner borders shall not be exploded neither the properties shall be changed without Owner's approval.
3 | Text Box | Page [1] Model | MAK | 2
4 | Call-out | Page [1] Model | MAK | Fill in EX and PN nos.
5 | Typewritten Text | Page [1] Model | Nabeel | Smoking
6 | Callout | Page [1] Model | Bernard.Grace | Make sure annotations are visible
7 | Callout | Page [1] Model | Bernard.Grace | This is 677 . Is there 27 unshaded? Where is owner parking?
8 | Callout | Page [1] Model | Bernard.Grace | (Double Storey Option)
9 | Callout | Page [1] Model | Bernard.Grace | This is a temporary access spur taken from Roundabout by TTSJV
10 | Callout | Page [1] Model | Bernard.Grace | Consider access road/turnaround to off load personnel for training
11 | Callout | Page [1] Model | Bernard.Grace | What is this access for?
12 | Callout | Page [1] Model | Bernard.Grace | Fire fighting capabilities and fire rating of facilities to be identified. Ensure compliance to API RP 753 for portable buildings (such as portacabins, trailers) and to comply with Chevron Fire Protection Manual Appendix H-Building Sitting Assessments (FPM 6000H, issue 2007 or later, as applicable) Ref Document SS/370/PSM/425/SH which is included in Volume 3 of ITB document
13 | Callout | Page [1] Model | Bernard.Grace | STOREY
14 | Callout | Page [1] Model | Bernard.Grace | Please confirm MOC consideration of relocating Rack Room to this area will not impact the plan
15 | Call-out | Page [1] Model | Adel | Where is the New Control Building?