## 000-R-GAD-60002-002-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Robert.Kawitzki | align bubbles
2 | Callout | 1 | Robert.Kawitzki | apply radius bends on corners - typical comment
3 | Callout | 1 | Robert.Kawitzki | carparks typically supplied with sun shades?
4 | Text Box | 1 | Antony.Bentley | Comment as per sheet 1
5 | Callout | 1 | Robert.Kawitzki | emergency gate not main gate
6 | Callout | 1 | Robert.Kawitzki | maximize carpark area X as per M
7 | Callout | 1 | Bernard.Grace | Please include assembly points
8 | Callout | 1 | Robert.Kawitzki | story
9 | Callout | 1 | Bernard.Grace | Their are no coordinates to confirm proposed location of facilities
10 | Callout | 1 | Robert.Kawitzki | what are these roads for?
11 | Callout | 1 | Robert.Kawitzki | why not combine carparks P and W?