## 000-R-GAD-60002-002-RB-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | Page 1 | MAK | 000 - COMMON
2 | Call-out | Page 1 | MAK | Why the alignment of this title is different than the one in sheet 001? The Owner borders shall not be exploded neither the properties shall be changed without Owner's approval.
3 | Text Box | Page 1 | MAK | 2
4 | Call-out | Page 1 | MAK | Fill in EX and PN nos.
5 | Text Box | Page 1 | MAK | Critical Comment: Why the text font is changed?? The text styles are predefined in each border and shall not be changed.
6 | Callout | Page 1 | Bernard.Grace | qq
7 | Callout | Page 1 | Bernard.Grace | Is there a reason for the reduction of 58 parking positions from drawing 6002-001 as there is the same number of personnel working or is it just space?
8 | Callout | Page 1 | Bernard.Grace | Where is owner parking?
9 | Callout | Page 1 | Bernard.Grace | (Single Storey Option)
10 | Callout | Page 1 | Bernard.Grace | How is material moved or controlled between areas? Would a short access road between drop off and fenced aid material handling?
11 | Callout | Page 1 | Bernard.Grace | This is a temporary access spur taken from Roundabout by TTSJV
12 | Callout | Page 1 | Bernard.Grace | Where has the medical facility gone?
13 | Callout | Page 1 | Bernard.Grace | Fire fighting capabilities and fire rating of facilities to be identified. Ensure compliance to API RP 753 for portable buildings (such as portacabins, trailers) and to comply with Chevron Fire Protection Manual Appendix H-Building Sitting Assessments (FPM 6000H, issue 2007 or later, as applicable) Ref Document SS/370/PSM/425/SH which is included in Volume 3 of ITB document
14 | Callout | Page 1 | Bernard.Grace | What is this access for?
15 | Callout | Page 1 | Bernard.Grace | Needs to be reviewed in greater detail.Not sure it is viable
16 | Callout | Page 1 | Bernard.Grace | What is this?