## 000-R-GAD-60011-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 |  | 1 | AutoCAD SHX Text | - Above Ground Holding Tank SEWER TANK (2.000 LT)
2 |  | 1 | AutoCAD SHX Text | - AIR CONDITIONED (SPLIT TYPE UNIT 12.000 BTU)
3 |  | 1 | AutoCAD SHX Text | - ROOF WATER TANK 2.000 LITERS
4 |  | 1 | AutoCAD SHX Text | 3 THE TANK INLET AND OUTLET VALVES SHALL BE
5 |  | 1 | AutoCAD SHX Text | PEOPLE AND PERSONNEL
6 |  | 1 | AutoCAD SHX Text | POSITIONED AT 1mt FROM GROUND.
7 |  | 1 | AutoCAD SHX Text | - POWER GENERATOR 24 kW
8 |  | 1 | AutoCAD SHX Text | TRAINING CENTER
9 |  | 1 | AutoCAD SHX Text | 076551C-000R-DW-8210-008
10 |  | 1 | AutoCAD SHX Text | 1
11 |  | 1 | AutoCAD SHX Text | 1
12 |  | 1 | AutoCAD SHX Text | 1 ALL DIMENSIONS ARE IN MILLIMETERS.
13 |  | 1 | AutoCAD SHX Text | 2 TRAINING CENTER SHALL BE AUTONOMOUS WITH:
14 |  | 1 | AutoCAD SHX Text | 27-04-2018
15 |  | 1 | AutoCAD SHX Text | 45 Seat
16 |  | 1 | AutoCAD SHX Text | 45 Seat
17 |  | 1 | AutoCAD SHX Text | A/C
18 |  | 1 | AutoCAD SHX Text | BATHROOM
19 |  | 1 | AutoCAD SHX Text | EL+ 0.400m BOTTOM OF CONTAINER
20 |  | 1 | AutoCAD SHX Text | EL+ 2.820m TOP OF CONTAINER
21 |  | 1 | AutoCAD SHX Text | F.DE CARLI
22 |  | 1 | AutoCAD SHX Text | F.DECARLI/
23 |  | 1 | AutoCAD SHX Text | ISSUE FOR APPROVAL
24 |  | 1 | AutoCAD SHX Text | LEGEND:
25 |  | 1 | AutoCAD SHX Text | M. LUCARELLI
26 |  | 1 | AutoCAD SHX Text | MAIN ENTRANCE
27 |  | 1 | AutoCAD SHX Text | OFFICE
28 |  | 1 | AutoCAD SHX Text | POWER GENERATOR
29 |  | 1 | AutoCAD SHX Text | R.PETROSSIANS
30 |  | 1 | AutoCAD SHX Text | REMOVABLE WALL
31 |  | 1 | AutoCAD SHX Text | SEE NOTE 3
32 |  | 1 | AutoCAD SHX Text | SEWER TANK
33 |  | 1 | AutoCAD SHX Text | SEWER TANK
34 | Call-out | 1 | Adel | This is a typical drawing without location plan or details. The final drawing shall be submitted for owner approval. This comment is applicable to all sheets.
35 |  | 1 | AutoCAD SHX Text | TOTAL SEAT : 90 PEOPLE
36 |  | 1 | AutoCAD SHX Text | TOTAL SURFACE : 201.6 Sqm
37 |  | 1 | AutoCAD SHX Text | TRAINING ROOM
38 |  | 1 | AutoCAD SHX Text | TRAINING ROOM
39 |  | 1 | AutoCAD SHX Text | VIEW "A-A"
40 |  | 1 | AutoCAD SHX Text | VIEW "A-A"
41 |  | 1 | AutoCAD SHX Text | WAITING AREA
42 |  | 1 | AutoCAD SHX Text | WATER TANK