## 000-R-GAD-60016-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Call-out | Page [1] Model | Adel | The Junction location and type / design to be finalized and approved with all stakeholders including Alba. Controlled junction to be provided. Traffic Management, Method Statement and Risk Assessment to be prepared.
2 | Text Box | Page [1] Model | MAK | 000 - COMMON
3 | Call-out | Page [1] Model | MAK | Fill in EX and PN nos.
4 | Call-out | Page [1] Model | MAK | General Comment: 001 shall be entered when the drawing consists of only a single sheet. Otherwise, the total sheet number shall be entered.
5 | Text Box | Page [1] Model | MAK | General Comment: Why the text font is changed?? The text styles are predefined in each border and shall not be changed.