## 000-R-MST-60001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | Use the latest document template.
2 | Call-out | 1 | Mahdi Ali | Document type is incorrect.
3 | Call-out | 2 | MAK | Add the document title on the page header in all pages.
4 | Callout | 3 | Abdulla Al Ansari | Include a statement to say that the Contractor and their Sub-Contractors shall comply with the BMP ESIA recommendations applicable to TCF facilities, and shall be in line with IFC performance standards and relevant guidelines.
5 | Callout | 3 | Bernard.Grace | in accordance with BMP Volume 2 - Common Documents and requirements Exhibit 5 - Assistance to Owner (for Owner's Facilities)
6 | Callout | 3 | scott.hillman | Define "external works"
7 | Callout | 4 | scott.hillman | Correct spelling to NOGA
8 | Text Box | 4 | Antony.Bentley | Total surface area 5212m2 - 2606m2 each floor
9 | Callout | 4 | Bernard.Grace | in accordance with BMP Volume 2 - Common Documents and requirements Exhibit 5 - Assistance to Owner (for Owner's Facilities)
10 | Text Box | 4 | Antony.Bentley | Should the Owners Operations Office be included in 'A'? as per drg. R-GAD-60015-001 2,482m2 If not then where is it included?
11 | Text Box | 5 | scott.hillman | Provide definition of acronyms
12 | Callout | 5 | scott.hillman | What does "as optional by tie-in for package A" mean?
13 | Callout | 6 | Bernard.Grace | Any conflict is to be raised to CONTRACTOR/Owner
14 | Text Box | 6 | Antony.Bentley | 2
15 | Callout | 8 | Bernard.Grace | and Arabic to international standards
16 | Callout | 8 | Bernard.Grace | Lever handles shall be of the 'D' shape to prevent fouling of clothing (for doors) as per BMPS-R1.
17 | Callout | 8 | Bernard.Grace | For internal insulation in walls where sound reduction is required between rooms, the insulation shall contribute to the overall construction achieving a sound reduction of 55dB or better. in accordance with BMPS R1
18 | Callout | 9 | Bernard.Grace | Alarm (Gas Detection H2S)
19 | Text Box | 9 | Antony.Bentley | See Vol.2 - Exhibit 5 Clause 4.2
20 | Text Box | 9 | Antony.Bentley | General Comment : Owners Office buildings shall be provided with the following additional specification requirements: - offices are to be carpet tiled -office doors are to be lockable - external doors & windows are to be double glazed
21 | Callout | 11 | scott.hillman | Based on the layout drawings provide by the Contractor, this statement is not correct.
22 | Callout | 11 | scott.hillman | Based on the layout drawings provide by the Contractor, this statement is not correct.
23 | Callout | 15 | Bernard.Grace | inclusive of access and egress to permit cleaning and maintenanance
24 | Callout | 18 | Bernard.Grace | with shade protection
25 | Callout | 18 | Bernard.Grace | Potable water
26 | Callout | 18 | Bernard.Grace | be
27 | Callout | 18 | Bernard.Grace | ?
28 | Callout | 18 | Bernard.Grace | of
29 | Callout | 19 | Bernard.Grace | of
30 | Callout | 19 | Bernard.Grace | Where are the details on hot water for the washbasins, showers etc?
31 | Callout | 19 | Bernard.Grace | for what?
32 | Callout | 21 | Bernard.Grace | and in accordance with BAPCO practices
33 | Callout | 23 | Bernard.Grace | Water