## 000-R-PQP-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Why the reference documents are placed on the cover page? Why not inside the document?
2 | Text Box | 1 | steven.coyne | •It is a generic checklist/ not project specific and subsequently does not refer to specific Building (Concrete & Masonry) •Forms are non descriptive (Accepted, Not Accepted, Remarks). No tolerances or specific criteria (no blast wall requirements are labelled for checking) are included to aid reviewer. •These will not really help the construction crew with assuring the works are completed in accordance with the Quality Control Inspection Test, Procedure. •Is it possible to get building specific check forms . •No coordinates are included for the buildings..
3 | Text Box | 1 | 300060 | Item B2 mentions Preservation at Storage report needs to be added to this QCP to capture Preservation activities performed. If preservation not applicable please delete the preservation part.
4 | Callout | 2 | Bernard.Grace | Ensure forms attached to document are in the order shown in this table.
5 | Callout | 3 | Mahdi Ali | LEGENDS
6 | Callout | 3 | Bernard.Grace | Include Inspection (H,W,S) for this
7 | Cloud | 3 | Bernard.Grace | c
8 | Callout | 3 | Mahdi Ali | FIT THE DOCUMENT NUMBER IN ONE LINE. THIS IS IMPORANT FOR BAPCO FOR TAG CAPTURING AND CREATING RELATIONSHIP TO DOCUMENTS IN SMART PLANT FUSION.
9 | Callout | 3 | Bernard.Grace | Include the tolerances for slab finish, especially for equipment rooms and staircases
10 | Callout | 17 | 300060 | Are these section required? If so please add relevant check boxes