## 000-S-LSD-60001-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Bernard.Grace | RELATIVE TO
2 | Callout | 1 | Bernard.Grace | Bahrain Island Datum(BID)
3 | Call-out | 1 | Mahdi Ali | Incorrect drawing number. drawing number shall include the sheet numbers as well.
4 | Call-out | 1 | MAK | Enlarge the column
5 | Call-out | 1 | MAK | Use English language
6 | Text Box | 1 | MAK | General Comment: The latest drawing borders have been submitted to JV Directorate on April 2018. Please use the latest drawing borders that are part of the Homogenisation Procedure.
7 | Call-out | 1 | MAK | 000 - COMMON
8 | Call-out | 1 | MAK | General Comment: Texts shall always be written in UPPER case
9 | Callout | 1 | Robert.Kawitzki | EL is in meters hence use three decimal places Eg 3.300 Typ comment
10 | Callout | 1 | Robert.Kawitzki | Indicate pipe track area
11 | Callout | 1 | Robert.Kawitzki | ARE
12 | Text Box | 1 | Robert.Kawitzki | PLANT DATUM &COORDINATE SYSTEM
13 | Text Box | 1 | Robert.Kawitzki | AT
14 | Callout | 1 | Robert.Kawitzki | 000-A-PPN-60006-0001 SHT 001
15 | Text Box | 1 | Robert.Kawitzki | AT
16 | Callout | 1 | Robert.Kawitzki | Show EL at Phase 1 for natural soil typical comment
17 | Text Box | 1 | Robert.Kawitzki | Populate Drawing Form
18 | Callout | 1 | scott.hillman | This areas has been excluded from the site preparation as per Owner response to T870.
19 | Callout | 1 | scott.hillman | Existing road corridor has been retained at current levels.
20 | Callout | 1 | scott.hillman | HLPH was not part of the site preparation works.
21 | Callout | 1 | scott.hillman | Existing road corridor to refinery ha been retained at current levels.
22 | Callout | 1 | scott.hillman | There is currently no rip rap along this edge.
23 | Callout | 1 | scott.hillman | There is currently no rip rap along the edge of the sulphur block.
24 | Callout | 1 | scott.hillman | All areas inside the utilty area have been filled to a rough grade level of 2.8m only. No areas have been fillled to 3.125
25 | Callout | 1 | scott.hillman | This section was not included in site preparation
26 | Callout | 1 | scott.hillman | 3.1m high areas have been filled to 3.6m RGL.
27 | Callout | 1 | scott.hillman | RGL 3.6m
28 | Callout | 1 | scott.hillman | Existing fenceline and ground level have been retained as per the existing levels