## 000-S-MRQ-60003-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Abdul Rahim | Owener comments on Loading Arms specification were not included at all. Please add all owners comment before release of this ddocument, if there is a disagreement then discuss but do not ignore.
2 | Typewritten Text | 2 | Nabeel | Correct spelling of Berth
3 | Call-out | 3 | Edgardo | The data sheets and specifications attached to this requisition are the uncommented copies; Please ensure that documents attached to the requisition covers the Owner's comments that were previously provided during the particular document reviews
4 | Callout | 4 | Abdul Rahim | why all loading arms no 061LA6111. if this wrong, then the total L/As are 19 and below are 17
5 | Text Box | 5 | Francis L | Include BMPS-B11 - Shop inspection requirements
6 | Text Box | 8 | Edgardo | Please clarify the pages 8 to 13 - Are these part of Attachment 1 mentioned in Page 7; The contents of pages 8 to 10 only showed the list of equipment whereas the contents of pages 11 to 13 only showed the list of vendors; as is, it is difficult to understand the correlation of the information shown in these pages
7 | Text Box | 11 | Omran A | Few vendor names are repeated such as ABB, Murry Steam Turbine, Siemens, etc....
8 | Text Box | 11 | Omran A | Add a third column and specify the system name that the vendor supplies.
9 | Text Box | 14 | rgrasselli | ATTACHMENT 2 TO MATERIAL REQUISITION NO. 000-S-MRQ-60003-001 REV A
10 | Text Box | 21 | Edgardo | Please indicate the applicable Attachment number of this sheet
11 | Text Box | 23 | Omran A | at T-Head (# 2 WHARF)
12 | Text Box | 23 | Omran A | -From berth #1-4 : Add " at T-Head (# 2 WHARF). -From berth #5-6 : Add " at Island Wharf (# 1 WHARF).
13 | Text Box | 23 | Omran A | at Island Wharf (# 1 WHARF)
14 | Text Box | 24 | Francis L | Ensure that all relevant documents as listed in section 17 of BMPS-J6 are included
15 | Callout | 25 | Francis L | To be issued after FAT activity.
16 | Text Box | 25 | Abdul Majeed | J/B schedule dwg
17 | Text Box | 25 | Omran A | & control narative
18 | Text Box | 25 | Omran A | & System drawing
19 | Text Box | 25 | Abdul Majeed | Alarm & Trip Procedure
20 | Callout | 29 | Abdul Rahim | space
21 | Callout | 29 | Abdul Rahim | B.S.C
22 | Callout | 29 | Abdul Rahim | space
23 | Text Box | 30 | Omran A | Each loading arm shall be controlled independently, to be discussed with TTSJV
24 | Callout | 30 | Francis L | Failure of any one loading arm and the associated control system shall not adversely affect the full functionality of any other loading arm.
25 | Callout | 30 | Abdul Rahim | Provide dummy riser at berth for arm testing
26 | Callout | 30 | Abdul Rahim | for C3/C4 liquid and vapor arms, provide 1 1/2 " nozzle at the end of both outer arms
27 | Callout | 30 | Abdul Rahim | Pls explain quick connect, we need bolted flange
28 | Callout | 31 | Abdul Rahim | I would like to make this very clear, owner requirement each loading arms hydraulic pack is independent of each other. i.e if one loading arm hydrulic pack is out of service then all other loading arms in the same berth are in service
29 | Text Box | 31 | Omran A | Owner prefer to have AB PLC for the following reasons: -Owner has AMC with Rockwell automation. -Inventory & spare parts management as most of PLCs are AB.
30 | Callout | 31 | Abdul Rahim | Pls note all white L/A gasket seals should be suitable for MTBE
31 | Text Box | 31 | Abdul Majeed | SS316 Material
32 | Text Box | 31 | Omran A | TTSJV to clarify the usage of Radio/Wireless? Loading arms are critical and wireless application shall not be used. To be in-line with BMPS-J10, 6.1.
33 | Text Box | 32 | Abdul Rahim | Vendor to provide Operation and Maintenance manual , in addition to break down of arm testing i.e daily, weekly, monthly, 3 monthly , 6 monthly and yearly
34 | Text Box | 32 | Abdul Majeed | Training for Operation, Maintenace and Engineering
35 | Text Box | 33 | Omran A | add Owner Rep
36 | Callout | 33 | Abdul Rahim | add: client rep
37 | Callout | 33 | Abdul Rahim | add: client rep
38 | Callout | 33 | Abdul Rahim | add: client rep
39 | Text Box | 33 | Abdul Majeed | Maintenance Rep
40 | Text Box | 33 | Abdul Majeed | Maintenance Rep
41 | Text Box | 33 | Omran A | Automation, Instrumentation and Inst Mtce rep to be added when required.
42 | Callout | 34 | Abdul Rahim | I would like to make this very clear, owner requirement each loading arms hydraulic pack is independent of each other. i.e if one loading arm hydraulic pack is out of service then all other loading arms in the same berth are in service
43 | Callout | 35 | Abdul Rahim | UPS shall be design for 2 hours after power failure
44 | Text Box | 35 | foo.choo | For the Island Wharf and T-Wharf, they are steel frame structure. Hence there is no concrete block to support the MLAsc
45 | Text Box | 36 | Abdul Majeed | Fast connection knife / disconnection terminal blocks
46 | Callout | 37 | A Albalooshi | Please indicate the equivalent standard.
47 | Text Box | 37 | Omran A | and shall be in-line with BMPS-J14
48 | Text Box | 38 | Francis L | Include the requirement of acceptance testing as per BMPS-J6 and BMPS-B11 (Shop inspection requirements), which includes FATand SAT.
49 | Text Box | 39 | Omran A | For all Automation and Instrumentation based systems, Owner rep shall be involved in witnessing all inspections (to be in-line with BMPS-B11).
50 | Text Box | 42 | foo.choo | Maximum allowable crane weight (including the loads) on the wharf is 18 tonnes. Delivery and installation of the MLAs shall be from the sea side when the load exceeds the wharf capacity.
51 | Text Box | 42 | Omran A | All application software shall be loaded with perpectual license
52 | Callout | 44 | Abdul Rahim | check area clasification
53 | Text Box | 44 | Omran A | General comments: All Control Systems cards/modules shall be conformal coated for the purpose of protecting electronic circuits from harash envirmoents
54 | Text Box | 46 | Abdul Majeed | I/O signals simulation test
55 | Callout | 47 | Francis L | This shall be fully tested as part of FAT activity. Input and output signals shall be simulated via simulation panels with switches, lamps, etc. It shall be a Hold point.
56 | Text Box | 54 | Abdul Rahim | Comments on this page to be applied to all L/A
57 | Callout | 54 | foo.choo | To specify the design wind speed at operating and idle condition
58 | Callout | 54 | Abdul Rahim | this is not correct, should be as low as 1000 BPH
59 | Text Box | 54 | foo.choo | To include minimum vessel size
60 | Callout | 54 | Abdul Rahim | this not correct, some how owner comments are not take into account
61 | Callout | 54 | Abdul Rahim | Add; sour
62 | Text Box | 55 | foo.choo | Should be based on the smallest vessel about 2m.
63 | Text Box | 55 | foo.choo | These comments applies to all White/black products MLAs in Berth 1, 2 and 3
64 | Text Box | 55 | foo.choo | The fenders face is about 6m from the wharf facial
65 | Text Box | 55 | foo.choo | 3m for oil tankers based on PIANC recommendation
66 | Text Box | 58 | foo.choo | To include smallest vessel size
67 | Callout | 66 | Abdul Rahim | contractor
68 | Callout | 66 | Abdul Rahim | this should be as low as 100 BPH during cooling of the line
69 | Text Box | 94 | foo.choo | The smallest vessel at Berth 3 is 5,000 DWT
70 | Text Box | 95 | foo.choo | Current fender face is about 6m from the edge of platform
71 | Text Box | 95 | foo.choo | Only 3 MLAs in Berth 3
72 | Text Box | 95 | foo.choo | These comments applies to all Berth 3 MLAs
73 | Text Box | 99 | foo.choo | Only 3 MLAs in Berth 3
74 | Text Box | 103 | foo.choo | There are only 3 MLAs in Berth 3
75 | Text Box | 103 | foo.choo | 3m is not correct. The width of the fender beam is already 3m.
76 | Text Box | 106 | foo.choo | To specify minimum vessel size
77 | Text Box | 107 | foo.choo | Island wharf platform level is different from the T-wharf. Need to establish the platform level first.
78 | Text Box | 107 | foo.choo | There are only 3 MLAs each in Berth 5 and 6
79 | Text Box | 127 | foo.choo | The omment here applies to all MLAs in Berth 5 and 6
80 | Text Box | 127 | foo.choo | Data for B, C and D not printed
81 | Text Box | 127 | foo.choo | There are only 3 MLAs at Berth 5 and 6
82 | Text Box | 128 | Omran A | Add Panel No 061-UX- ??