## 000-S-MRQ-60008-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Omran A | (PRESSURE SWING ADSORPTION )
2 | Text Box | 15 | Ahmed Habib | Defenition of PURCHASER, SUPPLIER and OWNER/CONTRACTOR shall be reflected
3 | Text Box | 16 | Omran A | (Instrument and Electrical)
4 | Text Box | 18 | Omran A | and IFAT
5 | Text Box | 18 | Ahmed Habib | Automation Engineer shall be added
6 | Text Box | 18 | Ahmed Habib | CHAZOP shall be added
7 | Text Box | 18 | Abdul Majeed | Maintenance Rep
8 | Text Box | 18 | Ahmed Habib | Owner
9 | Text Box | 22 | Ahmed Habib | Refer and comply with BMPS-J9 and J14
10 | Text Box | 28 | Omran A | (loaded with perpetual application software)