## 000-S-MST-60002-001-R0-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | Mahdi Ali | MST is used for Method Statement documents and the title of the of this document is Technical Specification. Use document type 'TSP'
2 | Text Box | 2 | Sankara | How about soil electrical resisistivity measurements for C3/ C4 Area?
3 | Callout | 5 | Bernard.Grace | Format
4 | Callout | 6 | Bernard.Grace | The environment is to be protected and precautions are to be put in place to ensure that.
5 | Callout | 6 | Bernard.Grace | This is supposed to be the Technical Specification according to document title
6 | Text Box | 7 | Antony.Bentley | 000-A-PRO-50076-001 Site HSSE Procedure for Geotechnical Works
7 | Callout | 8 | Bernard.Grace | CONTRACTOR
8 | Callout | 9 | Bernard.Grace | are as follows:
9 | Callout | 10 | Bernard.Grace | CONTRACTOR
10 | Text Box | 10 | Omran A | General note: If data cables were found during trial holes then contractor shall follow BMPS-J-141512
11 | Text Box | 10 | Omran A | and also trial holes
12 | Text Box | 11 | Antony.Bentley | ed
13 | Callout | 11 | Bernard.Grace | CONTRACTOR should be coordinating this to ensure all required readings are obtained
14 | Callout | 12 | Bernard.Grace | Owner's Control Station indicated by CONTRACTOR
15 | Text Box | 12 | Omran A | Method Statement & Risk Assessment shall be prepared for all work/site activities
16 | Callout | 12 | Bernard.Grace | are
17 | Text Box | 12 | Omran A | and Risk Assessment
18 | Callout | 12 | Bernard.Grace | ensure
19 | Callout | 12 | Bernard.Grace | electronic
20 | Text Box | 18 | Antony.Bentley | where?
21 | Callout | 24 | Sankara | what is additional?
22 | Callout | 24 | Sankara | Clarify / rephrase this statement