## 000-S-MST-60004-001-R0
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | MAK | General Comment: For all documents, use the latest document template that is part of the Homogenisation Procedure.
2 | Text Box | 1 | Mahdi Ali | THIS DOCUMENT IS A SPECIFICATIN AND NOT A METHOD STATEMENT. THUS THE DOCUMENT TYPE SHALL BE 'TSP' AND NOT 'MST'. CHANGE ALL THE REFERENCES TO THIS DOCUMENT ACCORDIGNLY. HOWEVER, IF THIS DOCUMENT IS A METHOD STATEMENT THEN THE TITLE SHOULD BE CHANGED ACCORDINGLY
3 | Callout | 6 | Chandrahasan D | Check the Coordinates OR WGS-84-UTM 39N OR AIN AL ABD UTM 39N Datum
4 | Callout | 8 | Chandrahasan D | Conversion factors for converting coordinates from UTM Zone 39N, Ain Al Abd Datum to WGS-84 UTM Zone 39N and vice versa to be provided as part of the topography survey.
5 | Callout | 8 | Chandrahasan D | Is it refererring to UTM Zone 39N coordinates - Ain Al ABD datum OR WGS84. Be specific
6 | Callout | 8 | Chandrahasan D | Provide updated drawing references
7 | Callout | 11 | Chandrahasan D | Consider revising it to minimum six months validity.
8 | Callout | 16 | Chandrahasan D | Include a section for tie-ins Survey requirements