## 000-S-PQP-50012-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | steven.coyne | On concrete compression tests, slump tests. There is a lack of detail contain in the recording of this activity and criteria/ methods to be applied when applicable. Please update the criteria to ASTM C31 or ASTM C39 or MS-1700.01 or whatever specification is be being used in this activity.
2 | Text Box | 1 | Erwin.Lugue | To include: -Procedure & forms for issuing/closing non-conformance inspection reports -Notice period of inspections
3 | Cloud+ | 3 | Erwin.Lugue | A (for approval)
4 | Text Box | 4 | steven.coyne | A
5 | Pen | 4 | steven.coyne | •
6 | Text Box | 4 | steven.coyne | add a reference
7 | Text Box | 4 | steven.coyne | Criteria is missing MS-1700.01, also sample types cube, cylindrical
8 | Text Box | 7 | steven.coyne | REMOVE BLANK PAGE