## 000-S-PQP-50014-001-RA-CS
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Text Box | 1 | 300060 | QCP needs to identify Preservation for equipment after completion and this needs to be a "Witness Point" for Owner Check sheet for Preservation to be added to QCP
2 | Text Box | 3 | Roelie Pretorius | Include sheet for package units with details below: All manual, actuated and control valves properly installed, tested, greased and ready for service All actuated valves have been function tested and fail in the correct position. Relief valves are fitted, tagged and certified with valid calibration date. All instruments, safety devices and alarms are tested and ready for service. Electrical grounding is installed as per specification for skid, equipment, junction boxes, cable tray and instruments. Lube / Seal oil systems are flushed to specification. Lube / Seal system have been filled to the correct level with the correct specified lubricant. Fuel system is complete, new filters fitted and system has been flushed to specification. Cooling system is complete flushed and filled with the correct coolant mixture. All manufacturersâ€™ static checks have been completed. Gearbox is complete, clean and filled with the correct grade lubricant. Sump has been drained and refilled with the correct grade lubricant. Gas sealing system is complete. All temporary screens and filters have been removed. Filters are clean and have the correct elements fitted. Check that all vents and drains are complete and all spades / spec blinds are fitted in the correct orientation. Equipment vibration mounts are free and set correctly. Vessels are clean and filled to the correct level with the correct fluid specified. Access covers, manways are secured with proper gaskets and bolt torquing, with acceptance of proper check sheets completed. Confirm dampers are correctly charged. Equipment is free to rotate and direction of rotation is clearly marked. All guards are fitted; skid is clean and free from debris. All support systems and auxiliary equipment are complete and available. Permanent / temporary fire detection / protection systems are installed and operable. All electrical installations are correct and ready for service: junction boxes, power cables, control cables, lighting systems, DC systems All field and gauge board mounted instruments have been checked and calibrated as necessary. Confirm that PCS input / output functions have been checked / calibrated. Equipment Package is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. All specific equipment function tests have been completed. All equipment is properly tagged to match drawings and Vendor Start Up and Operating Manual. Vendor recommended pre-start up checks have been carried out in accordance with Vendor Start Up and Operating Manual. Manufacturer's recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant dynamic commissioning procedure.
3 | Text Box | 4 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - PLATFORMS/LADDERS/HANDRAILS - BLINDED NOZZLES / MANWAY (ADECUATE STUDBOLTS/GASKET/DAVIT) - EARTHING/GROUNDING CONNECTION CHECK - TEMPORARY BLIND / SUPPORTS REMOVALS (AS APPLICABLE)
4 | Text Box | 4 | giovanny.rodriguez | - ACHE WINTERIZATION CHECK (AS APPLICABLE) - MOTOR AREA AND HEADERS AREA MAINTENANCE PLATFORMS/HANDRAILS - MOTOR POWER/CONTROL WIRE CONNECTIONS - VIBRATION SENSORS/SWITCH CONNECTIONS UP TO JB - BLADES FIXED/TIGHTENING CHECK - EARTHING/GROUNDING CONNECTION CHECK
5 | Text Box | 4 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - PLATFORMS/LADDERS/HANDRAILS - BLINDED NOZZLES / MANWAY (ADECUATE STUDBOLTS/GASKET/DAVIT) - EARTHING/GROUNDING CONNECTION CHECK - TEMPORARY BLIND / SUPPORTS REMOVALS (AS APPLICABLE)
6 | Callout | 4 | giovanny.rodriguez | ADD PULLEYS & SHAFTS
7 | Callout | 5 | Fernando.Perez | Alignment & Balacing
8 | Callout | 5 | hyunjin.paeng | Add : - Check Bolt tightening for Foundation and Flange - Check Motor power & Control wire connection - Check Cooling line arrangement - Check Baseplate leveling and Grouting
9 | Callout | 5 | hyunjin.paeng | Add : - Check Bolt tightening for Foundation and Flange - Check Motor power & Control wire connection - Check Cooler and cooling Line arrangement - Check Surge Control valve
10 | Callout | 5 | Fernando.Perez | Alignment & Balacing
11 | Callout | 6 | hyunjin.paeng | Add : - Check Bolt tightening for Foundation and Flange - Check Motor power & Control wire connection - Check Blow off Valve - Check Damper and expansion joint
12 | Callout | 6 | hyunjin.paeng | Add : - Check Bolt tightening for Foundation and Flange - Check Motor power & Control wire connection - Check Cooler and cooling Line arrangement - Check Load & Unload Valve - Check Pulsation Dampener
13 | Callout | 7 | Fernando.Perez | Balacing
14 | Callout | 7 | Fernando.Perez | Balacing
15 | Callout | 7 | hyunjin.paeng | Typical Comments : - Check Bolt tightening for Mounting plate and Flange - Check Trip and Governor valve connection - Check Steam inlet , outlet and drain Line arrangement - Casing and Trip Valve Drain
16 | Callout | 7 | Fernando.Perez | Balacing
17 | Callout | 7 | Fernando.Perez | - Seal Installation / Retaining Clips Removal - Fixation Bolts TIGHTENING
18 | Text Box | 8 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - BLINDED NOZZLES (ADECUATE STUDBOLTS/GASKET) - TEMPORARY BLIND / SUPPORTS REMOVALS (AS APPLICABLE) - ADECUATE INTERMEDIATE FIX BOLTS (STACKED HX CASE)
19 | Callout | 9 | Fernando.Perez | replace by "DESICANT" As desicant can be Silica Gel, Activated Alumina or Molecular Sieve and Acc. BMPS-S11 for instrument air dryers Activated Alumina shall be used
20 | Callout | 9 | Fernando.Perez | - Pre & Post Filters cartridges Installation - CONTROL Panel wiring CONNECTION & checking - Compressed Air shall be available for Commisioning
21 | Text Box | 11 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - PLATFORMS/LADDERS/HANDRAILS - PEEPHOLES / INSPECTION SIGHT GLASS Installation - EARTHING/GROUNDING CONNECTION CHECK
22 | Text Box | 11 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - PLATFORMS/LADDERS/HANDRAILS - BLINDED NOZZLES / MANWAY (ADECUATE STUDBOLTS/GASKET/DAVIT) - EARTHING/GROUNDING CONNECTION CHECK
23 | Callout | 11 | Sang.Hwang | Add proper installation check of PVSV, Emergency Vent Cover etc. in accordance with Installation Manual
24 | Text Box | 12 | giovanny.rodriguez | - MOTOR AREA AND TOP AREA MAINTENANCE PLATFORMS/HANDRAILS - MOTOR POWER/CONTROL WIRE CONNECTIONS - MOTOR ROTATING DIRECTION - VIBRATION SENSORS/SWITCH CONNECTIONS UP TO JB - BLADES FIXED/TIGHTENING CHECK - EARTHING/GROUNDING CONNECTION CHECK
25 | Callout | 12 | 300060 | W
26 | Text Box | 12 | giovanny.rodriguez | - INSULATION / PP SHIELD CHECK (AS APPLICABLE) - PLATFORMS/LADDERS/HANDRAILS - PEEPHOLES / INSPECTION SIGHT GLASS Installation - EARTHING/GROUNDING CONNECTION CHECK
27 | Callout | 12 | 300060 | w
28 | Callout | 13 | hyunjin.paeng | Add : - Check Motor power wire connection - Check Rotating direction - Check Mounting plate leveling
29 | Callout | 13 | 300060 | 1st fill W
30 | Callout | 15 | 300060 | W
31 | Callout | 15 | 300060 | W
32 | Callout | 16 | hyunjin.paeng | Typical Comments : - Check Bolt tightening for Foundation and Flange - Check Motor power & Control wire connection - Check Baseplate leveling and Grouting - Casing Vent & Drain
33 | Text Box | 16 | 300060 | H
34 | Callout | 16 | 300060 | Preservation
35 | Text Box | 16 | 300060 | W
36 | Text Box | 16 | 300060 | W
37 | Callout | 16 | hyunjin.paeng | Check railway alignment
38 | Callout | 17 | 300060 | 1st Fill W
39 | Text Box | 19 | Newlito Diaz | GENERAL COMMENT: TORQUING and FLANGE MANAGEMENT during static equipment final box-up and/or rotating equipment final alignment are to be considered in the sheets or a dedicated sheet?
40 | Call-out | 19 | Newlito Diaz | Consider to provide space format indicating Sub-system to allow early walk downs and PC&C on discreet sections of a system when necessary (General Comment for majority of forms).
41 | Text Box | 19 | Newlito Diaz | UNIT: SUP:
42 | Text Box | 19 | Newlito Diaz | SYSTEM: SUB-SYSTEM:
43 | Text Box | 19 | David.Jimenez | Please update forms according to the revised scope
44 | Call-out | 20 | Newlito Diaz | (General Comment for majority of forms): Is this section still necessary to be signed by sub-contractor during PC&C/Start-Up? Consider removing to provide space for licensor/vendor sign-off.
45 | Text Box | 20 | Roelie Pretorius | Vent and drain valves have been exercised. Check that correct filter element is installed. On duplex filters, check changeover valves for freedom of operation. Spades and spec blinds are removed or in correct position as required. Man-way(s) closed out with correct gaskets, bolting, and torque. Flame arrestor installed if applicable with bird screen. Over pressure / vacuum protection device(s) function tested. Settlement, tank calibration and /or vendor requirements have been approved. Records and certificates are attached. Regulatory authorities have approved tank calibration (if required, i.e., export tanks).
46 | Text Box | 21 | Roelie Pretorius | Add following checks: Heat Exchanger and associated pieces are still free from damage, clean, and free from obstructions. Preservation was maintained up to this â€œBâ€ check and has subsequently been removed for this check, including but not limited to drain valves periodic opening to avoid trapped liquids. Attached pipe work is correctly installed and leak tested. Flanged connections are tightened with correct permanent gaskets, bolting, and torque. Spades and spec blinds are removed or in correct position as required. If applicable, internal inspection has been carried out and Manway(s) and/or nozzles have been closed out with correct permanent gaskets, bolting, and torque. Sliding feet are free to move. All manual and control valves are properly installed, tested, greased, and ready for service. Vent and drain valves have been exercised. Equipment has been completely drained through all the low point valves. All instruments are function tested and ready for service. All safety devices (PSVs, alarms, etc.) are function tested and ready for service.
47 | Text Box | 23 | Roelie Pretorius | Add following checks for typical compressor: Preliminary Alignment of the Compressor and Driver (i.e., reduction gear, electric motor, etc.) has been recorded and accepted. (Attach Pre-Alignment Report) Grouting has been completed. Final Alignment of the Compressor and Driver (with suction / discharge piping tightened) has been recorded and accepted (Attach Final Alignment Report). Soft-foot check was completed and accepted. Cooling system is clean and operable. All gas and cooling water piping is properly installed as per P&IDs, it has been flushed and is clean. Drain / vent connections are complete. There is adequate supply of cooling water to oil cooler. Lube / Seal oil system is clean and operable. All piping and tubing connections have been properly flushed, cleaned, and reinstated as per P&IDs. Oil tank and oil run down tank are filled to the correct level with clean oil of the correct grade Correct and clean new filter elements are installed. Oil pump alignments and power connections have been completed. All safety and control instrumentation is operable. Oil heater connection is complete / operational. Pressure Lubrication System is clean and operable. Lubrication system has been reinstated in accordance with the P&IDs. Lubrication lines have been blown with instrument air, they are clean and unplugged. Lubricator is filled with oil and check proper supply to all lubricated points by rotating the crank by hand. Mechanical (Dry) Gas Seal System is clean and operable. Confirm Seal gas system is complete as per the P&ID, buffer gas supply (Nitrogen / Air) is available at the proper pressure / temperature. Separation gas (nitrogen or air) is available at the proper pressure and temperature. Correct seal gas filters have been installed. Shaft packing or Seals are installed. Seal chamber drains have been installed and no liquids are present. All internal components and clearances have been checked: crankshaft, valves, piston, cylinder, suction volume bottle, piston-rod seals at cylinder stuffing box, etc. Driver run in has been completed, vibration and temperatures were acceptable. Driver rotates in the correct direction. Transmission / gearbox has been installed and it contains oil up to the correct level. Compressor shaft is free to turn. Note one full turn is adequate without lube oil at bearings. Ensure adequate supply of lube oil at bearings. Piping alignment to the compressor nozzles is completed as per project requirements. Piping is connected to compressor without stress. Coupling(s) are installed and all bolts are properly tightened. Coupling guards and all associated vents and drains are installed. Suction filter / screen / protection mesh have been installed, as per filter data sheet. All temporary suction strainers required are in place and are the correct rating. Compressor casing drains are operational and correctly lined up to closed drain system. Compressor discharge pressure relief valves are correctly lined up to flare, set at correct pressure, and valid calibration certificate is available. Anti-surge valve (ASV) is properly installed and stroke check was performed. All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. Heat Exchanger and associated appurtenances / internals are undamaged and clean. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. Sight glasses have been checked. Electrical grounding is installed as per specification. All temporary supports, screens, filters, and plugs, pertaining to cleaning and any other Pre-Commissioning activities have been removed. Spare parts relevant to the equipment and their accessories are available. Compressor is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual. Manufacturerâ€™s recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.
48 | Text Box | 25 | Roelie Pretorius | Add the following checks: Fan /air blower Unit, skid and base structure, vibration dampers and all components fitted in accordance with suppliersâ€™ documentation, undamaged, in good and clean condition. Lubrication system is correctly installed as per P&IDâ€™s, is clean and operable. Lube oil filter and filter element are correctly installed and clean. Pulley alignment and belt tension have been verified. V-belt tension adjustment has been verified if applicable. Belt rating is sufficient. Preliminary alignments have been checked as per manufacturerâ€™s specs for shaft bearings, belts, motor pulleys, and belt tensions correct. Coupling rating is sufficient. Safety guard is provided and is easily removable for belt tensioning / replacement. Safety guard is of non-sparking type and is easily removable. Air intake system and air filters are clean and correctly installed. Electric motor and electrical items have been verified, tested and energized. Impeller is centered in housing, moves freely by hand and static balance satisfactory. Impeller key is installed. Manual control damper is fitted (if required) functional and left in open state. All bearing greased and grease zerks installed correctly and clean All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. Fan / Blower is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. Vendor recommended pre-start up checks have been carried out in accordance with Vendor Start Up and Operating Manual. Confirm equipment is ready for dynamic commissioning as specified on relevant dynamic commissioning procedure.
49 | Text Box | 26 | Roelie Pretorius | See compressor checks added and add applicable for turbine
50 | Text Box | 28 | Roelie Pretorius | Add checks below: Heat Exchanger and associated pieces are still free from damage, clean, and free from obstructions. Preservation was maintained up to this â€œBâ€ check and has subsequently been removed for this check, including but not limited to drain valves periodic opening to avoid trapped liquids. Attached pipe work is correctly installed and leak tested. Flanged connections are tightened with correct permanent gaskets, bolting, and torque. Spades and spec blinds are removed or in correct position as required. If applicable, internal inspection has been carried out and Manway(s) and/or nozzles have been closed out with correct permanent gaskets, bolting, and torque. Sliding feet are free to move. All manual and control valves are properly installed, tested, greased, and ready for service. Vent and drain valves have been exercised. Equipment has been completely drained through all the low point valves. All instruments are function tested and ready for service. All safety devices (PSVs, alarms, etc.) are function tested and ready for service.
51 | Text Box | 39 | Roelie Pretorius | Add checks below: Tank is still free from damage, clean, and free from obstructions. Preservation was maintained up to this check and has subsequently been removed for this check. Vent and drain valves have been exercised. Check that correct filter element is installed. On duplex filters, check changeover valves for freedom of operation. Spades and spec blinds are removed or in correct position as required. Man-way(s) closed out with correct gaskets, bolting, and torque. Flame arrestor installed if applicable with bird screen. Over pressure / vacuum protection device(s) function tested. Settlement, tank calibration and /or vendor requirements have been approved. Records and certificates are attached. Regulatory authorities have approved tank calibration (if required, i.e., export tanks).
52 | Text Box | 41 | Roelie Pretorius | Add checks below: Equipment and associated appurtenances are undamaged and clean Equipment internals; valves, tubes, coils, baffles, etc., are installed in accordance with specifications, drawings and/or vendor/licensor instructions. Refractory dry out is complete, inspected and accepted. All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. All power and controls for the Boiler have been tested and are now set to off and locked out. All blinds called for are in place, and all blinds to be removed are pulled. Electrical grounding is installed as per specification. Clearance for expansion has been verified and accepted. All temporary supports, screens, filters, and plugs, pertaining to cleaning and any other Pre-Commissioning activities have been removed. Spare parts relevant to the equipment and their accessories are available. Boiler is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. If required; Legal, Governmental, Regulatory and/or Licensor inspections, requirements and approvals have been met. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual. Manufacturerâ€™s recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.
53 | Text Box | 42 | Roelie Pretorius | Add checks below: Equipment and associated appurtenances are undamaged and clean. View ports / peep holes are unobstructed. Refractory dry out is complete. Refractory was inspected for cracks after dryout and accepted. Burner tips and air passages are clean. Peep hole, Flame eyes and Snuffing connections are free. All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. All power and controls for the Fired Heater have been tested, including ignitors and ignition burners, and are now set to off and locked out. All blinds called for are in place, and all blinds to be removed are pulled. Electrical grounding is installed as per specification. Clearance for expansion has been verified and accepted. All temporary supports, screens, filters, and plugs, pertaining to cleaning and any other Pre-Commissioning activities have been removed. Spare parts relevant to the equipment and their accessories are available. Fire heater is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual. Manufacturerâ€™s recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.
54 | Text Box | 44 | Newlito Diaz | VENDOR PACKAGE SAT CHECKED
55 | Text Box | 44 | Newlito Diaz | VENDOR PACKAGE IN-LINE STRAINER CHECKED
56 | Text Box | 45 | Newlito Diaz | FUEL FILLING COMPLETED
57 | Text Box | 46 | Newlito Diaz | SOLO-RUN TEST COMPLETED
58 | Text Box | 46 | Newlito Diaz | BUMP TEST COMPLETED
59 | Text Box | 47 | Newlito Diaz | LUBRICATION INJECTION LINES, INJECTION POINTS CHECKED AND CHARGING COMPLETED
60 | Text Box | 47 | Newlito Diaz | SYSTEM LINE CLEANING OF ALL UTILITIES COMPLETED
61 | Text Box | 47 | Newlito Diaz | ACCUMULATOR FILLING/CHARGING COMPLETED
62 | Text Box | 55 | Roelie Pretorius | Include checks below: Equipment and associated appurtenances are undamaged and clean (i.e., Heating/cooling coils, filters, chillers, air handling unit, air condensers, ductwork, etc.). All duct and field mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. All Fire Dampers and Shut-off Dampers are operational. All power and controls have been tested, including thermostats and temperature control devices, and are now set to off and locked out. Electrical grounding is installed as per specification Electric Heaters are complete and ready for service Fan Internals clear and fans ready for service. All belts, couplings and guards are installed/ tensioned correctly. HVAC System Tests have been performed and accepted. Attach reports not covered by another check sheet. If required; Legal, Governmental, Regulatory and/or Licensor inspections, requirements and approvals have been met. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual, and with vendor assistance if required. Manufacturerâ€™s recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.
63 | Text Box | 55 | Newlito Diaz | SAT COMPLETED
64 | Callout | 63 | Mohamed Ayyash | Need to add: Vessels, separators, incinerators, LPG bullets, blowers, re boilers, steam generators
65 | Text Box | 73 | Roelie Pretorius | Vent and drain valves have been exercised. Sliding feet are free to move. Check operability of all valves associated with vessel. Spades and spec blinds are removed or in correct position as required. Manway(s) and/or nozzles closed out with correct permanent gaskets, bolting, and torque. Flanged connections are tightened with correct permanent gaskets, bolting, and torque. Over pressure / vacuum protection device(s) are function tested.
66 | Text Box | 73 | Roelie Pretorius | Licensors and/or regulatory entities have witnessed internal inspection (if required).
67 | Text Box | 73 | Roelie Pretorius | Internals are completed/reinstated; including but not limited to support screens, trays, Packing, Demister pad(s), Distributor(s), Downcomers, Draw off tray(s), Swirl deck, Schoepentoeter, etc.)
68 | Text Box | 73 | Newlito Diaz | BOLT TORQUING COMPLETED
69 | Text Box | 74 | Roelie Pretorius | Attached pipe work is correctly installed and leak tested. Flanged connections are tightened with correct permanent gaskets, bolting, and torque. Spades and spec blinds are removed or in correct position as required. ISliding feet are free to move. All manual and control valves are properly installed, tested, greased, and ready for service. Vent and drain valves have been exercised. Equipment has been completely drained through all the low point valves. All instruments are function tested and ready for service. All safety devices (PSVs, alarms, etc.) are function tested and ready for service.
70 | Text Box | 75 | Newlito Diaz | BOLT TORQUING COMPLETED (IF APPLICABLE)
71 | Text Box | 76 | Roelie Pretorius | Preliminary Alignment of the Compressor and Driver (i.e., reduction gear, electric motor, etc.) has been recorded and accepted. (Attach Pre-Alignment Report) Grouting has been completed. Final Alignment of the Compressor and Driver (with suction / discharge piping tightened) has been recorded and accepted (Attach Final Alignment Report). Soft-foot check was completed and accepted. Cooling system is clean and operable. All gas and cooling water piping is properly installed as per P&IDs, it has been flushed and is clean. Drain / vent connections are complete. There is adequate supply of cooling water to oil cooler. Lube / Seal oil system is clean and operable. All piping and tubing connections have been properly flushed, cleaned, and reinstated as per P&IDs. Oil tank and oil run down tank are filled to the correct level with clean oil of the correct grade Correct and clean new filter elements are installed. Oil pump alignments and power connections have been completed. All safety and control instrumentation is operable. Oil heater connection is complete / operational. Pressure Lubrication System is clean and operable. Lubrication system has been reinstated in accordance with the P&IDs. Lubrication lines have been blown with instrument air, they are clean and unplugged. Lubricator is filled with oil and check proper supply to all lubricated points by rotating the crank by hand. Mechanical (Dry) Gas Seal System is clean and operable. Confirm Seal gas system is complete as per the P&ID, buffer gas supply (Nitrogen / Air) is available at the proper pressure / temperature. Separation gas (nitrogen or air) is available at the proper pressure and temperature. Correct seal gas filters have been installed. Shaft packing or Seals are installed. Seal chamber drains have been installed and no liquids are present. All internal components and clearances have been checked: crankshaft, valves, piston, cylinder, suction volume bottle, piston-rod seals at cylinder stuffing box, etc. Driver run in has been completed, vibration and temperatures were acceptable. Driver rotates in the correct direction. Transmission / gearbox has been installed and it contains oil up to the correct level. Compressor shaft is free to turn. Note one full turn is adequate without lube oil at bearings. Ensure adequate supply of lube oil at bearings. Piping alignment to the compressor nozzles is completed as per project requirements. Piping is connected to compressor without stress. Coupling(s) are installed and all bolts are properly tightened. Coupling guards and all associated vents and drains are installed.
72 | Text Box | 77 | Roelie Pretorius | Suction filter / screen / protection mesh have been installed, as per filter data sheet. All temporary suction strainers required are in place and are the correct rating. Compressor casing drains are operational and correctly lined up to closed drain system. Compressor discharge pressure relief valves are correctly lined up to flare, set at correct pressure, and valid calibration certificate is available. Anti-surge valve (ASV) is properly installed and stroke check was performed. All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. Heat Exchanger and associated appurtenances / internals are undamaged and clean. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. Sight glasses have been checked. Electrical grounding is installed as per specification. All temporary supports, screens, filters, and plugs, pertaining to cleaning and any other Pre-Commissioning activities have been removed. Spare parts relevant to the equipment and their accessories are available. Compressor is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual. Manufacturerâ€™s recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.
73 | Text Box | 78 | Roelie Pretorius | Preservation was maintained up to this check and has subsequently been removed for this check. Fan /air blower Unit, skid and base structure, vibration dampers and all components fitted in accordance with suppliersâ€™ documentation, undamaged, in good and clean condition. Lubrication system is correctly installed as per P&IDâ€™s, is clean and operable. Lube oil filter and filter element are correctly installed and clean. Pulley alignment and belt tension have been verified. V-belt tension adjustment has been verified if applicable. Belt rating is sufficient. Preliminary alignments have been checked as per manufacturerâ€™s specs for shaft bearings, belts, motor pulleys, and belt tensions correct. Coupling rating is sufficient. Safety guard is provided and is easily removable for belt tensioning / replacement. Safety guard is of non-sparking type and is easily removable. Air intake system and air filters are clean and correctly installed. Electric motor and electrical items have been verified, tested and energized. Impeller is centered in housing, moves freely by hand and static balance satisfactory. Impeller key is installed. Manual control damper is fitted (if required) functional and left in open state. All bearing greased and grease zerks installed correctly and clean All field and gauge board mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. Fan / Blower is complete with all auxiliaries and ancillary equipment necessary for safe and proper functional test. Vendor recommended pre-start up checks have been carried out in accordance with Vendor Start Up and Operating Manual. Confirm equipment is ready for dynamic commissioning as specified on relevant dynamic commissioning procedure.
74 | Callout | 79 | Fernando.Perez | Drains, governor
75 | Text Box | 86 | Roelie Pretorius | Internals are completed/reinstated; including but not limited to support screens, trays, Packing, Demister pad(s), Distributor(s), Downcomers, Draw off tray(s), Swirl deck, Schoepentoeter, etc.) Vessel and associated pieces are still free from damage, clean, and free from obstructions. Licensors and/or regulatory entities have witnessed internal inspection (if required). Preservation was maintained up to this check and has subsequently been removed for this check. Vent and drain valves have been exercised. Sliding feet are free to move. Check operability of all valves associated with vessel. Spades and spec blinds are removed or in correct position as required. Manway(s) and/or nozzles closed out with correct permanent gaskets, bolting, and torque. Flanged connections are tightened with correct permanent gaskets, bolting, and torque. Over pressure / vacuum protection device(s) are function tested.
76 | Text Box | 87 | Newlito Diaz | ALL RELATED FUNCTION TESTS COMPLETED
77 | Text Box | 88 | Newlito Diaz | ALL RELATED FUNCTION TESTS COMPLETED
78 | Text Box | 100 | Roelie Pretorius | Equipment and associated appurtenances are undamaged and clean (i.e., Heating/cooling coils, filters, chillers, air handling unit, air condensers, ductwork, etc.). All duct and field mounted instruments have been checked and calibrated as necessary. PCS input / output functions have been checked / calibrated. All manual and automatic control valves are properly installed, tested, set in the correct position (on-off), greased and ready for service. All instruments, safety devices and alarms have been tested and are ready for service. All Fire Dampers and Shut-off Dampers are operational. All power and controls have been tested, including thermostats and temperature control devices, and are now set to off and locked out. Electrical grounding is installed as per specification Electric Heaters are complete and ready for service Fan Internals clear and fans ready for service. All belts, couplings and guards are installed/ tensioned correctly. HVAC System Tests have been performed and accepted. Attach reports not covered by another check sheet. If required; Legal, Governmental, Regulatory and/or Licensor inspections, requirements and approvals have been met. Vendor recommended pre-start up checks have been carried out, in accordance with Vendor Start Up and Operating Manual, and with vendor assistance if required. Manufacturer's recommendation for preparation to start has been reviewed and there are no conflicts between that document and the commissioning procedure. Equipment is ready for dynamic commissioning as specified on relevant and approved dynamic commissioning procedure.