## 000-S-STD-50001-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | NTS
2 | Callout | 1 | Chandrahasan D | Verify the practicality of applying bitumen coating for cast in situ construction. Construction point of it, the catch basin will be in place first with associated piping and concrete will be poured after that.
3 | Callout | 1 | Chandrahasan D | Joint filler??
4 | Text Box | 1 | Salman Almajed | BMPS-Q-50701
5 | Text Box | 1 | Salman Almajed | Add description for the drawings
6 | Text Box | 1 | Salman Almajed | BMPS-SD-S-78325
7 | Callout | 1 | Joon Cho | <Add> 8) FOR SEWER SYSTEMS, SEE BMPS-S-50813 (typical comment)
8 | Cloud+ | 1 | MAK | Text style and height should not be changed. Every border has predefined styles and heights and shall be used as outline in BMPS-A8.
9 | Cloud+ | 1 | MAK | Delete
10 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
11 | Callout | 1 | Joon Cho | 'Max. 150 mm' as per para. 12.3.2 of BMPS-S1 (typical comment)
12 | Callout | 1 | Chandrahasan D | Verify the requirement of pipe material specification in standard dwg. If required to be shown in standard dwg, make sure the connection details are available for other type of pipe materials.
13 | Cloud+ | 1 | Salman Almajed | Use reinforced concrete for traffic areas.
14 | Text Box | 1 | Antony.Bentley | HPP - ...
15 | Text Box | 1 | Antony.Bentley | RTS - Reinforced Thermosetting Resin
16 | Callout | 1 | Mahdi Ali | USE UPPER CASE
17 | Callout | 1 | Chandrahasan D | Joint sealant shall be oil (Hydrocarbon) resistant type
18 | Cloud+ | 1 | MAK | 000 - COMMON
19 | Text Box | 1 | Salman Almajed | BMPS-Q-50701
20 | Text Box | 1 | Antony.Bentley | Abbreviations
21 | Text Box | 1 | Salman Almajed | BMPS-S-50806
22 | Callout | 1 | Chandrahasan D | Specify Minimum Mix strength required, in not specified in Standard notes
23 | Text Box | 1 | Antony.Bentley | D
24 | Callout | 1 | Chandrahasan D | Verify requirement of pipe material annotations in all locations.
25 | Text Box | 1 | Antony.Bentley | Add all standard detail drawings in this transmittal
26 | Cloud+ | 1 | MAK | Move to 2nd line of the title
27 | Callout | 1 | Erwin.Lugue | Covers shall be designed as per the minimum loads mentioned in BPMS A1 sec 10.7.10
28 | Text Box | 1 | Antony.Bentley | LPP - ...