## 000-S-STD-50005-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Cloud+ | 1 | MAK | Move to 2nd line of the title
2 | Cloud+ | 1 | Salman Almajed | <Recommendation> Please use closed stirrups or provide a better arrangement.
3 | Text Box | 1 | Salman Almajed | BMPS-Q-50701
4 | Text Box | 1 | Salman Almajed | Add description for the drawings
5 | Cloud+ | 1 | MAK | Delete
6 | Cloud+ | 1 | MAK | Text style and height should not be changed. Every border has predefined styles and heights and shall be used as outline in BMPS-A8.
7 | Cloud+ | 1 | Erwin.Lugue | in S.I. units
8 | Callout | 1 | Salman Almajed | The detail shows two diameters for stirrups. Please remove one of them.
9 | Callout | 1 | Erwin.Lugue | Indicate the required clearance from the pipe
10 | Text Box | 1 | Erwin.Lugue | Ensure that all the manholes are adequately designed without excessive settlement & checked for uplift (if necessary)
11 | Text Box | 1 | Salman Almajed | BMPS-S-50806
12 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
13 | Text Box | 1 | Erwin.Lugue | Around pipe openings shall have similar additional detail in wall reinforcement
14 | Callout | 1 | Erwin.Lugue | Covers shall be designed as per the minimum loads mentioned in BPMS A1 sec 10.7.10
15 | Cloud+ | 1 | MAK | 000 - COMMON
16 | Cloud+ | 1 | MAK | NTS
17 | Text Box | 1 | Antony.Bentley | General note: All comments made on drawing no. 50003-001 are applicable to the similar details on this sheet