## 000-S-STD-50007-001-RA
ID | Subject | Page | Author | Comments | JV Replies | Comment included (Y/N) | Bapco closure (Y/N)
1 | Callout | 1 | Joon Cho | System is not match up with BMPS-SD-S-10279, Contractor to re-check
2 | Text Box | 1 | MAK | General Comment: All the texts in drawings shall be searchable and in UPPERCASE. Text fonts and styles shall be as per BMPS-A8.
3 | Cloud+ | 1 | MAK | NTS
4 | Text Box | 1 | Antony.Bentley | Preformed semi-circular channel sections of vitrified clay or upvc
5 | Cloud+ | 1 | Salman Almajed | Provide dimensions for the ladder
6 | Text Box | 1 | Antony.Bentley | General note: All comments made on drawing no. 50003-001 are applicable to the similar details on this sheet
7 | Cloud+ | 1 | MAK | Move to 2nd line of the title
8 | Callout | 1 | Erwin.Lugue | Covers & frames shall be designed as per the minimum loads mentioned in BPMS A1 sec 10.7.10
9 | Cloud+ | 1 | MAK | 000 - COMMON
10 | Text Box | 1 | Salman Almajed | BMPS-S-50806
11 | Text Box | 1 | Salman Almajed | HYDROPHILIC
12 | Text Box | 1 | Salman Almajed | BMPS-Q-50701
13 | Text Box | 1 | Erwin.Lugue | Ensure that all the manholes are adequately designed without excessive settlement & checked for uplift (if necessary)
14 | Callout | 1 | Joon Cho | with double seal type rim seals as per 11.4.2 of BMPS-S1
15 | Cloud+ | 1 | MAK | Text style and height should not be changed. Every border has predefined styles and heights and shall be used as outline in BMPS-A8.
16 | Text Box | 1 | Salman Almajed | Add description for the drawings
17 | Cloud+ | 1 | MAK | Delete